Monitoring Report

###### PUBLICATION DATE 14.10.2020
VERSION v. 1.1 
RELATED SUPPORT - TEMPLATE GUIDE Monitoring Report v. 1.1

This document contains the following Sections

Key Project Information

0 - Description of project

0 - Implementation of project

0 - Description of monitoring system applied by the project

0 - Data and parameters

0 - Calculation of SDG Impacts

0 - Safeguards Reporting

0 - Stakeholder inputs and legal disputes

### KEY PROJECT INFORMATION

##### Programme of Activity Information – (delete below table if N/A)

| GS ID of Programme | GS3110 |
| --- | --- |
| Title of Programme | Nepal Biogas Support Program-PoA |
| Version of POA-DD applicable to this monitoring report | For Crediting Period 1: GS PoA Passport: version 05 CDM PoA-DD: version 14.0 For Crediting Period 2: GS PoA Passport: version 03 CDM PoA-DD: version 17.0 |
| Name and GS ID of fully Validated CPA/VPAs (i.e. non-compliance check) | GS3109: Nepal Biogas Support Program – CPA 1: 20,000 digesters GS3113: Nepal Biogas Support Program - CPA 2: 19,927 digesters GS 3114: Nepal Biogas Support Program - CPA 3: 19,959 digesters GS3116: Nepal Biogas Support Program - CPA 4: 19,970 digesters |

##### Key Project Information

| GS ID (s) of Project (s) | GS3109, GS 3113; GS 3114, GS 3116, GS 3566, GS 6393, GS 6394, GS 7508, GS 7509, GS10739 |
| --- | --- |
| Title of the project (s) covered by monitoring report | Nepal Biogas Support Program – CPA 1: 20,000 digesters Nepal Biogas Support Program - CPA 2: 19,927 digesters Nepal Biogas Support Program - CPA 3: 19,959 digesters Nepal Biogas Support Program - CPA 4: 19,970 digesters Nepal Biogas Support Program - CPA 5: 19,842 digesters Nepal Biogas Support Program - CPA 6: 18,504 digesters Nepal Biogas Support Program - CPA 7: 18,392 digesters Nepal Biogas Support Program - CPA 8: 19,445 digesters Nepal Biogas Support Program – CPA 9: 17,304 digesters Nepal Biogas Support Program-CPA 10: 10,589 digesters |
| Version number of the PDD/VPA-DD (s) applicable to this monitoring report | For Crediting Period 1: CPA-2: GS Passport version 02, CDM CPA-DD version 03 CPA-3: GS Passport version 02, CDM CPA-DD version 03 CPA-4: GS Passport version 03, CDM CPA-DD version 03 CPA-5: VPA-DD Version 07 CPA-6: VPA-DD Version 07 CPA-7: VPA-DD Version 07 CPA-8: VPA-DD Version 02 CPA-9: VPA-DD version 02 For Crediting Period 2: CPA-1: version 03 CPA-2: Version 04 CPA-3: Version 04 CPA-4: Version 04 CPA-5: Version 11 CPA-10: version 03.1 |
| Version number of the monitoring report | 03 |
| Completion date of the monitoring report | 09/12/2022 |
| Date of project design certification | CPA-1: 14/08/2015 CPA-2: 14/08/2015 CPA-3: 14/08/2015 CPA-4: 14/08/2015 CPA-5: 24/12/2018 CPA-6: 24/12/2018 CPA-7: 24/12/2018 CPA-8: 23/09/2019 CPA-9: 23/09/2019 CPA-10: 28/09/2020 |
| Date of Last Annual Report | N/A |
| Monitoring period number | For Crediting Period 1: CPA-2: 08 CPA-3: 08 CPA-4: 08 CPA-5: 05 CPA-6: 05 CPA-7: 05 CPA-8: 03 CPA-9: 03 Fore Crediting Period 2: CPA 1: 02 CPA 2: 02 CPA 3: 02 CPA 4: 02 CPA 5: 02 CPA 10:02 |
| Duration of this monitoring period | 01/01/2021 to 31/12/2021 |
| Project Representative | Alternative Energy Promotion Centre (AEPC) |
| Host Country | Nepal |
| Activity Requirements applied | Community Services Activities Renewable Energy Activities Land Use and Forestry Activities/Risks & Capacities N/A |
| Methodology (ies) applied and version number | For Crediting Period 1 AMS.I.E. Switch from Non-Renewable Biomass for Thermal Applications by the User (version 04) For Crediting Period 2 AMS.I.E. Switch from Non-Renewable Biomass for Thermal Applications by the User (version 09) |
| Product Requirements applied | GHG Emissions Reduction & Sequestration Renewable Energy Label N/A |

##### Table 1 - Sustainable Development Contributions Achieved

| Sustainable Development Goals Targeted | SDG Impact | Amount Achieved | Units/ Products |
| --- | --- | --- | --- |
| SDG 13 Climate Action | Emissions Reductions | Crediting Period 1 (CP1): CPA-2: 19,954 CPA-3: 21,624 CPA-4: 21,083 CPA-5: 39,966 CPA-6: 53,868 CPA-7: 50,947 CPA-8: 59,357 CPA-9: 54,228 Total: 321,027 Crediting Period 2 (CP2) : CPA-1: 61,560 CPA-2: 41,716 CPA-3: 44,908 CPA-4: 43,978 CPA-5: 24,316 CPA-10: 32,018 Total: 248,496 | GS-CERs |
| SDG3 Good Health and Well Being | 3.9.1 Mortality rate attributed to household and ambient air pollution (Users’ perception on reduction in indoor air pollution) | CPA-1: 97.61% CPA-2: 100% CPA-3: 97.77% CPA-4: 93.26% CPA-5: 98.90% CPA-6: 97.70% CPA-7: 96.43% CPA-8: 100% CPA-9: 98.93% CPA-10:100% | % households |
|  | 3.9.1 Mortality rate attributed to household and ambient air pollution (Users’ perception on reduction in health problem) | CPA-1: Eye infection: 94.05%, Respiratory disease: 89.29% Cough: 86.90% Fire related Injury: 91.67% CPA-2: Eye infection: 100%, Respiratory disease: 93.02% Cough: 94.19% Fire related Injury: 93.02% CPA-3: Eye infection: 98.92% Respiratory disease: 90.32% Cough: 89.25% Fire related Injury: 93.55% CPA-4: Eye infection: 91.01% Respiratory disease: 97.64% Cough: 77.53% Fire related Injury: 83.15% CPA-5: Eye infection: 97.80% Respiratory disease: 93.41% Cough: 90.11% Fire related Injury: 100% CPA-6: Eye infection: 95.40% Respiratory disease: 95.40% Cough: 78.16% Fire related Injury: 85.06% CPA-7: Eye infection: 95.24% Respiratory disease: 88.10% Cough: 88.10% Fire related Injury: 88.10% CPA-8: Eye infection: 98.90% Respiratory disease: 98.90% Cough: 92.31% Fire related Injury: 95.60% CPA-9: Eye infection: 97.80% Respiratory disease: 88.30% Cough: 88.30% Fire related Injury: 88.30% CPA-10: Eye infection: 95.51% Respiratory disease: 91.01% Cough: 94.38% Fire related Injury: 96.63% | % households |
|  | 3.9.1 Mortality rate attributed to household and ambient air pollution (User’s perception in Time saving for the cooking (reduce exposure to indoor air pollution)) | % response for; Men; Women; Children. CPA-1; 40.48; 98.81; 17.86. CPA-2; 48.84; 100; 27.91. CPA-3; 25.81; 96.77; 21.51. CPA-4; 46.07; 97.75; 16.85. CPA-5; 36.26; 100; 29.67. CPA-6; 42.86; 100; 17.86. CPA-7; 38.10; 100; 25. CPA-8; 30.77; 100; 23.08. CPA-9; 51.06; 100; 19.15. CPA-10; 39.33; 100; 5.62. | % households |
|  | 3.9.2 Mortality rate attributed to unsafe water, unsafe sanitation and lack of hygiene (exposure to unsafe Water, Sanitation and Hygiene for All (WASH) services) (Users’ perception on connection of toilet to biogas): | CPA-1: 67.86% CPA-2: 74.42% CPA-3: 63.44% CPA-4: 89.89% CPA-5: 85.71% CPA-6: 87.36% CPA-7: 79.76% CPA-8: 85.71% CPA-9: 79.79% CPA-10: 96.63% | % households |
|  | 3.9.3 Mortality rate attributed to unintentional poisoning (Users perception in reduction of chemical fertilizers) | CPA-1: Farmyard manure: 32.41% Bioslurry: 100%, Urea: 33.10%, DAP: 40.39% Potash: 58.06% CPA-2: Farmyard manure: 28.68% Bioslurry: 100%, Urea: 38.54%, DAP: 0% Potash: 50.00% CPA-3: Farmyard manure: 31.47% Bioslurry: 100% Urea: 27.27% DAP: 29.35% Potash: 41.18% CPA-4: Farmyard manure: 30.62% Bioslurry: 100% Urea: 37.42% DAP: 0% Potash: 58.62% CPA-5 Farmyard manure: 32.09% Bioslurry: 100% Urea: 41.51% DAP: 35.74% Potash: 33.26% CPA-6: Farmyard manure: 30.65% Bioslurry: 100% Urea: 35.52% DAP: 36.65% Potash: 46.43% CPA-7: Farmyard manure: 27.25% Bioslurry: 100% Urea: 37.99% DAP: 39.33% Potash: 51.23% CPA-8: Farmyard manure: 28.59% Bioslurry: 100% Urea: 25.66% DAP: 28.23% Potash: 33.33% CPA-9: Farmyard manure: 33.13% Bioslurry: 100% Urea: 39.12% DAP: 42.38% Potash: 56.08% CPA-10: Farmyard manure: 32.59% Bioslurry: 100% Urea: 31.36% DAP: 50.00% Potash: 0% | % |
| SDG 7 Affordable and Clean Energy | 7.1.2 Proportion of population with primary reliance on clean fuels and technology (Share of digesters operational) (%) | CPA 1: 83.60 %. CPA-2: 86.43% CPA-3: 93.51% CPA-4: 91.12% CPA-5: 93.55% CPA-6: 87.42% CPA-7: 83.19% CPA-8: 91.67% CPA-9: 94.11% CPA 10: 82.12% | % operational |
|  | 7.1.2 Proportion of population with primary reliance on clean fuels and technology (Users’ perception on time saving due to project for firewood collection) | % for; Men; Women; Children. CPA-1; 73.81; 95.24; 10.71. CPA-2; 65.12; 98.84; 29.07. CPA-3; 49.46; 97.85; 18.28. CPA-4; 65.17; 98.88; 15.73. CPA-5; 73.63; 100; 17.58. CPA-6; 83.93; 100; 14.29. CPA-7; 63.10; 100; 26.19. CPA-8; 62.64; 98.90; 7.69. CPA-9; 70.21; 100; 19.15. CPA-10; 49.44; 98.88; 5.62. | % |
|  | 7.1.2 Proportion of population with primary reliance on clean fuels and technology (Number of people trained to promote Biogas plants): | 75 (last MP as no training conducted in this MP) | Number |

##### Table 2 – Product Vintages

|  |  | Amount Achieved |  |  |
| --- | --- | --- | --- | --- |
| Start Dates | End Dates | GS | … | … |
| CPA-1 |  |  |  |  |
| 01 Jan 2021 | 31 Dec 2021 | 61,560 |  |  |
| CPA-2 (CP 1) |  |  |  |  |
| 1 Jan 2021 | 7 May 2021 | 19,954 |  |  |
| CPA-2 (CP 2) |  |  |  |  |
| 08 May 2021 | 31 Dec 2021 | 41,716 |  |  |
| CPA-3 (CP1) |  |  |  |  |
| 1 Jan 2021 | 7 May 2021 | 21,624 |  |  |
| CPA-3 (CP2) |  |  |  |  |
| 08 May 2021 | 31 Dec 2021 | 44,908 |  |  |
| CPA-4 (CP1) |  |  |  |  |
| 1 Jan 2021 | 7 May 2021 | 21,083 |  |  |
| CPA-4 (CP2) |  |  |  |  |
| 08 May 2021 | 31 Dec 2021 | 43,978 |  |  |
| CPA-5 (CP1) |  |  |  |  |
| 1 Jan 2021 | 24 Aug 2021 | 39,966 |  |  |
| CPA-5 (CP2) |  |  |  |  |
| 25 Aug 2021 | 31 Dec 2021 | 24,316 |  |  |
| CPA-6 |  |  |  |  |
| 1 Jan 2021 | 31 Dec 2021 | 53,868 |  |  |
| CPA-7 |  |  |  |  |
| 1 Jan 2021 | 31 Dec 2021 | 50,947 |  |  |
| CPA-8 |  |  |  |  |
| 1 Jan 2021 | 31 Dec 2021 | 59,357 |  |  |
| CPA-9 |  |  |  |  |
| 1 Jan 2021 | 31 Dec 2021 | 54,228 |  |  |
| CPA-10 |  |  |  |  |
| 1 Jan 2021 | 31 Dec 2021 | 32,018 |  |  |

#### SECTION A. DESCRIPTION OF PROJECT

##### A.1. General description of project

The Biogas Support Program (BSP) aims at implementing household biogas applications. These applications displace firewood and fossil fuels with biogas from animal waste and human excreta. The biogas is used as a fuel for cooking, therefore the displacement of non-renewable biomass (NRB) is counted as emission reduction under the Clean Development Mechanism (CDM) and Gold Standard (GS).Target group under the BSP are households with at least one head of cattle (generally cows or buffalos) who currently use non-renewable biomass (firewood) for cooking purpose. The baseline of the PoA considers only non-renewable biomass replaced through household biogas applications. Only households previously using non-renewable biomass are eligible to the PoA.

The technologies used in this CPA are household biogas digesters with a sludge and gas holding capacity range of up to 10 m3. The different sizes of the digesters that would be included in the programme would be of 2, 4, 6, 8 and 10 m3. The programme uses only one design i.e. GGC 2047 model. The biogas digesters are based on a uniform technical design and are manufactured and installed following established technical standards in Nepal. The digester itself is a closed underground container made of concrete or other materials.

Nepal Biogas Support Program-PoA was registered on 31st January 2013. The reference number of the PoA is 9572. The first renewable period of the PoA is 31st January 2013 to 30th January 2020. The duration of PoA is from 22nd June 2007 to 21st June 2035. The PoA is renewed for 2nd renewal period.

Biogas Model GGC 2047

Biogas plants constructed under this PoA comprise of three major components; the inlet, the digester and the outlet, aligned in a straight line. All these structures are prepared of masonry walls of bricks or stones, depending upon the material availability. Digester unit is an underground chamber where the mixture of animal dung and water is fed into where the microbial activity takes place. The microbes act upon the dung (the substrate) under anaerobic conditions to release methane and carbon dioxide. The methane released from the digester is collected at the dome which is connected to gas hose pipe fitted at turret at the center of the dome. Biogas collected at the dome dispensed to biogas stove through this gas hose pipe via turret. Once the gas pressure is sufficient in dome, it exerts pressure to the slurry in the digester and slurry is released from the outlet.

This monitoring report includes ten CPAs (CPA-1 to CPA-10) proposed for verification. For Crediting Period 1, eight monitoring report (CPA 2 to CPA 9) of Eighth monitoring period  are proposed for verification, whereas for crediting period 2 monitoring report includes 6 CPAs (CPA-1, CPA-2, CPA-3, CPA-4, CPA-5 and CPA-10) of second monitoring period for the verification. Before this monitoring period, already 7 periodic verifications were completed for the PoA.

##### This monitoring report includes 6 CPAs (CPA-1, CPA-2, CPA-3, CPA-4, CPA-5 and CPA-10) proposed for verification in second monitoring period for the second period of the PoA. Before this monitoring period, already 7 periodic verifications were completed for the PoA. A.2. Location of project

All the specific case CPAs are implemented across Nepal in different districts. The geographical coordinates of Nepal are:

Latitude – North 26.20 degree to North 30.45 degree

Longitude – East 80.07 degree to East 88.20 degree

The table below provides the overview of the biogas digesters implemented under different CPAs incorporated in this monitoring report in different districts of Nepal.

| SN | Districts | CPA-1 | CPA-2 | CPA-3 | CPA-4 | CPA-5 | CPA-6 | CPA-7 | CPA-8 | CPA-9 | CPA-10 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Achham | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 15 |
|  | Arghakhanchi | 78 | 26 | 30 | 21 | 7 | 15 | 25 | 34 | 49 | 4 |
|  | Baglung | 38 | 46 | 62 | 52 | 35 | 15 | 62 | 32 | 59 | 52 |
|  | Baitadi | 8 | 1 | 0 | 0 | 2 | 3 | 3 | 0 | 12 | 0 |
|  | Bajhang | 12 | 36 | 33 | 10 | 148 | 0 | 0 | 0 | 14 | 19 |
|  | Bajura | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 26 |
|  | Banke | 374 | 489 | 361 | 412 | 434 | 520 | 403 | 514 | 268 | 269 |
|  | Bara | 416 | 382 | 356 | 310 | 458 | 338 | 299 | 426 | 291 | 244 |
|  | Bardiya | 498 | 510 | 599 | 804 | 900 | 1099 | 875 | 735 | 732 | 379 |
|  | Bhaktapur | 64 | 89 | 67 | 4 | 14 | 11 | 12 | 15 | 12 | 9 |
|  | Bhojpur | 0 | 7 | 27 | 18 | 9 | 0 | 1 | 4 | 0 | 0 |
|  | Chitwan | 1114 | 1042 | 935 | 844 | 870 | 889 | 690 | 584 | 301 | 184 |
|  | Dadeldhura | 18 | 1 | 0 | 1 | 15 | 4 | 0 | 1 | 59 | 9 |
|  | Dailekh | 15 | 24 | 12 | 0 | 0 | 0 | 3 | 9 | 3 | 102 |
|  | Dang | 345 | 801 | 751 | 1230 | 1327 | 827 | 548 | 494 | 570 | 272 |
|  | Darchula | 45 | 11 | 21 | 0 | 18 | 14 | 9 | 60 | 54 | 33 |
|  | Dhading | 581 | 720 | 876 | 852 | 631 | 558 | 701 | 463 | 626 | 487 |
|  | Dhankuta | 7 | 53 | 78 | 25 | 17 | 10 | 91 | 60 | 14 | 25 |
|  | Dhanusa | 51 | 26 | 31 | 17 | 33 | 44 | 38 | 98 | 229 | 77 |
|  | Dolakha | 126 | 112 | 170 | 230 | 76 | 128 | 90 | 62 | 220 | 52 |
|  | Dolpa | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Doti | 0 | 4 | 1 | 31 | 25 | 0 | 3 | 4 | 6 | 0 |
|  | Gorkha | 451 | 434 | 376 | 410 | 347 | 338 | 616 | 309 | 850 | 670 |
|  | Gulmi | 55 | 87 | 61 | 55 | 37 | 19 | 43 | 30 | 19 | 13 |
|  | Humla | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Ilam | 460 | 624 | 468 | 559 | 373 | 287 | 934 | 487 | 197 | 215 |
|  | Jajarkot | 1 | 0 | 0 | 6 | 6 | 0 | 0 | 37 | 0 | 46 |
|  | Jhapa | 2770 | 2391 | 1369 | 874 | 925 | 666 | 1027 | 963 | 684 | 582 |
|  | Jumla | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Kailali | 730 | 1011 | 1080 | 1571 | 1630 | 3119 | 2172 | 2738 | 1367 | 507 |
|  | Kalikot | 24 | 25 | 11 | 8 | 15 | 9 | 17 | 46 | 24 | 19 |
|  | Kanchanpur | 757 | 776 | 746 | 808 | 914 | 1523 | 766 | 1140 | 1056 | 323 |
|  | Kapilbastu | 333 | 211 | 401 | 353 | 263 | 86 | 239 | 298 | 261 | 47 |
|  | Kaski | 1051 | 769 | 899 | 773 | 594 | 225 | 384 | 610 | 768 | 221 |
|  | Kathmandu | 87 | 40 | 17 | 36 | 16 | 10 | 35 | 20 | 24 | 24 |
|  | Kavre | 506 | 393 | 677 | 575 | 478 | 434 | 480 | 299 | 483 | 334 |
|  | Khotang | 5 | 6 | 7 | 20 | 5 | 9 | 8 | 2 | 8 | 0 |
|  | Lalitpur | 192 | 125 | 92 | 141 | 109 | 81 | 72 | 28 | 85 | 21 |
|  | Lamjung | 673 | 537 | 582 | 620 | 409 | 255 | 281 | 594 | 588 | 366 |
|  | Mahottari | 82 | 87 | 87 | 92 | 138 | 147 | 180 | 343 | 109 | 79 |
|  | Makwanpur | 788 | 1739 | 2363 | 1860 | 2652 | 1944 | 835 | 1019 | 1042 | 690 |
|  | Morang | 1078 | 827 | 562 | 447 | 547 | 308 | 552 | 566 | 703 | 384 |
|  | Mugu | 0 | 2 | 2 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Mustang | 7 | 4 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |
|  | Myagdi | 41 | 36 | 85 | 67 | 33 | 14 | 12 | 52 | 7 | 0 |
|  | Nawalparasi | 746 | 614 | 649 | 477 | 432 | 287 | 350 | 315 | 363 | 224 |
|  | Nuwakot | 188 | 194 | 64 | 375 | 277 | 395 | 470 | 153 | 260 | 254 |
|  | Okhaldhunga | 8 | 2 | 0 | 18 | 44 | 37 | 46 | 29 | 67 | 132 |
|  | Palpa | 457 | 380 | 392 | 402 | 401 | 358 | 256 | 466 | 326 | 135 |
|  | Panchthar | 108 | 64 | 78 | 33 | 36 | 61 | 90 | 49 | 37 | 3 |
|  | Parbat | 24 | 33 | 25 | 18 | 9 | 8 | 19 | 34 | 29 | 27 |
|  | Parsa | 106 | 62 | 25 | 51 | 72 | 144 | 59 | 170 | 63 | 92 |
|  | Pyuthan | 47 | 53 | 79 | 119 | 80 | 31 | 137 | 180 | 63 | 58 |
|  | Ramechhap | 116 | 66 | 66 | 77 | 181 | 41 | 29 | 63 | 200 | 313 |
|  | Rasuwa | 0 | 52 | 46 | 69 | 112 | 133 | 65 | 10 | 38 | 0 |
|  | Rautahat | 169 | 164 | 124 | 123 | 160 | 270 | 225 | 224 | 160 | 164 |
|  | Rolpa | 0 | 0 | 15 | 20 | 6 | 5 | 30 | 37 | 85 | 12 |
|  | Rukum | 0 | 4 | 10 | 0 | 5 | 0 | 0 | 0 | 0 | 78 |
|  | Rupandehi | 587 | 358 | 419 | 237 | 287 | 61 | 278 | 235 | 146 | 72 |
|  | Salyan | 15 | 24 | 28 | 28 | 2 | 12 | 22 | 8 | 78 | 21 |
|  | Sankhuwasabha | 4 | 32 | 42 | 27 | 28 | 26 | 30 | 72 | 20 | 1 |
|  | Saptari | 9 | 13 | 17 | 14 | 16 | 8 | 84 | 154 | 166 | 91 |
|  | Sarlahi | 295 | 308 | 309 | 299 | 365 | 320 | 290 | 423 | 270 | 191 |
|  | Sindhuli | 581 | 584 | 502 | 527 | 443 | 1055 | 1213 | 1455 | 644 | 624 |
|  | Sindhupalchowk | 100 | 54 | 186 | 145 | 126 | 293 | 220 | 186 | 102 | 135 |
|  | Siraha | 37 | 34 | 66 | 31 | 42 | 22 | 11 | 126 | 113 | 115 |
|  | Solukhumbu | 3 | 13 | 23 | 27 | 5 | 5 | 0 | 0 | 48 | 0 |
|  | Sunsari | 458 | 240 | 157 | 133 | 131 | 57 | 157 | 134 | 137 | 84 |
|  | Surkhet | 139 | 216 | 185 | 234 | 210 | 116 | 153 | 199 | 504 | 213 |
|  | Syangja | 580 | 453 | 513 | 497 | 433 | 289 | 403 | 452 | 581 | 244 |
|  | Tanahu | 1125 | 1135 | 1321 | 1575 | 1117 | 198 | 384 | 424 | 639 | 387 |
|  | Taplejung | 4 | 0 | 3 | 16 | 5 | 16 | 4 | 27 | 65 | 14 |
|  | Terhathum | 15 | 31 | 51 | 45 | 30 | 2 | 22 | 95 | 2 | 1 |
|  | Udayapur | 191 | 228 | 267 | 209 | 277 | 305 | 839 | 543 | 304 | 105 |
|  | Total | 19999 | 19927 | 19959 | 19970 | 19842 | 18504 | 18392 | 19445 | 17304 | 10,589 |

##### A.3. Reference of applied methodology

For Crediting Period 1 (CP1):

Methodology used: AMS-I.E. ver. 4 - Switch from non-renewable biomass for thermal applications by the user

Reference: https://cdm.unfccc.int/methodologies/DB/XA6RFKB3QM9T8S6ELI0V4P8SY8RR2U

For Crediting Period 2 (CP2):

Methodology used: AMS-I.E. ver. 9 - Switch from non-renewable biomass for thermal applications by the user

Reference: https://cdm.unfccc.int/methodologies/DB/XA6RFKB3QM9T8S6ELI0V4P8SY8RR2U

##### A.4. Crediting period of project

CPA-1 (CP2): 31/01/2020 to 30/01/2027

CPA-2 (CP1): 08/05/2014 – 07/05/2021

CPA-2 (CP2): 08/05/2021 to 07/05/2028

CPA-3 (CP1): 08/05/2014 – 07/05/2021

CPA-3 (CP2): 08/05/2021 to 07/05/2028

CPA-4 (CP1): 08/05/2014 – 07/05/2021

CPA-4 (CP2): 08/05/2021 to 07/05/2028

CPA-5 (CP1): 25/08/2014 – 24/08/2021

CPA-5 (CP2): 25/08/2021 to 24/08/2028

CPA-6 (CP1): 08/07/2015 – 07/07/2022

CPA-7 (CP1): 08/07/2015 – 07/07/2022

CPA-8 (CP1): 15/02/2017 – 14/02/2024

CPA-9 (CP1): 15/05/2019 - 14/05/2026

CPA -10 (CP2): 18/05/2020 to 17/05/2027

#### SECTION B. IMPLEMENTATION OF PROJECT

##### B.1. Description of implemented project

This monitoring report presents the details of eight CPAs (CPA#2 to CPA#9) proposed for verification in this monitoring period. All the digesters included in these eight CPAs are the household biogas digesters based on the anaerobic digestion technologies. The CPAs have the digesters installed with capacity ranging from 2 m3 to 10 m3.

AEPC maintains the record of installed biogas digesters. Each biogas installed under different CPAs is identified with its unique dome gas pipe number and hence the uniqueness of the identity is maintained for each digester. Since all the digesters implemented under all CPAs of the PoA are centrally maintained, possibility of the double counting of the digesters between and within CPAs is avoided.

CPA-1:

This CPA is part of the Nepal Biogas Support Program-Programme of Activity (PoA). This CPA includes 19,999 digesters which were implemented between 22/06/2007 and 18/03/2009. The table below provides the overview of digesters implemented under CPA-1.

| Region Size | Terai | Hill | Mountain or Remote Hill | Total |
| --- | --- | --- | --- | --- |
| 4 m3 | 416 | 2,690 | 5 | 3,111 |
| 6 m3 | 9,393 | 6,128 | 96 | 15,617 |
| 8 m3 | 1,141 | 118 | 4 | 1,263 |
| 10 m3 | 5 | 3 | 0 | 8 |
| Total | 10,955 | 8,939 | 105 | 19,999 |

CPA-2:

This CPA is part of the Nepal Biogas Support Program-PoA. This CPA includes 19,927 digesters which were implemented between 19/03/2009 and 9/03/2010. The table below provides the overview of digesters implemented under CPA.

| Region Size | Terai | Hill | Mountain or Remote Hill | Total |
| --- | --- | --- | --- | --- |
| 2 m3 | 8 | 248 | 0 | 256 |
| 4 m3 | 491 | 3,482 | 19 | 3,992 |
| 6 m3 | 8,993 | 5,624 | 124 | 14,741 |
| 8 m3 | 852 | 83 | 1 | 936 |
| 10 m3 | 2 | 0 | 0 | 2 |
| Total | 10,346 | 9,437 | 144 | 19,927 |

CPA-3:

This CPA is part of the Nepal Biogas Support Program-PoA. This CPA includes 19,959 digesters which were implemented between 10/03/2010 and 19/02/2011. The table below provides the overview of digesters implemented under CPA.

| Region Size | Hill | Terai | Mountain or Remote Hill | Total |
| --- | --- | --- | --- | --- |
| 2 m3 | 1,279 | 38 | 0 | 1,317 |
| 4 m3 | 4,420 | 651 | 40 | 5,111 |
| 6 m3 | 4,977 | 7,710 | 120 | 12,807 |
| 8 m3 | 78 | 645 | 1 | 724 |
| Total | 10,754 | 9,044 | 161 | 19,959 |

CPA-4:

This CPA is part of the Nepal Biogas Support Program-PoA. This CPA includes 19,970 digesters which were implemented between 20/02/2011 and 28/02/2012. The table below provides the overview of digesters implemented under CPA.

| Region Size | Hill | Terai | Mountain or Remote Hill | Total |
| --- | --- | --- | --- | --- |
| 2 m3 | 694 | 20 | 17 | 731 |
| 4 m3 | 5,292 | 668 | 48 | 6,008 |
| 6 m3 | 4,691 | 7,784 | 58 | 12,533 |
| 8 m3 | 43 | 655 | 0 | 698 |
| Total | 10,720 | 9,127 | 123 | 19,970 |

CPA-5:

This CPA is part of the Nepal Biogas Support Program-PoA. This CPA includes 19,842 digesters which were implemented between 29/02/2012 and 23/05/2013. The table below provides the overview of digesters implemented under CPA.

| Region Size | Hill | Terai | Mountain or Remote Hill | Total |
| --- | --- | --- | --- | --- |
| 2 m3 | 288 | 13 | 3 | 304 |
| 4 m3 | 4,932 | 622 | 161 | 5,715 |
| 6 m3 | 4,391 | 8,718 | 64 | 13,173 |
| 8 m3 | 58 | 591 | 1 | 650 |
| Total | 9,669 | 9,944 | 229 | 19,842 |

CPA-6:

This CPA is part of the Nepal Biogas Support Program-PoA. This CPA includes 18,504 digesters which were implemented between 24/05/2013 and 04/04/2014.Table below provides an overview of the digesters implemented under CPA.

| Region Size | Hill | Terai | Mountain or Remote Hill | Total |
| --- | --- | --- | --- | --- |
| 2 m3 | 86 | 2 | 0 | 88 |
| 4 m3 | 1,547 | 265 | 11 | 1,823 |
| 6 m3 | 5,965 | 9,772 | 52 | 15,789 |
| 8 m3 | 108 | 696 | 0 | 804 |
| Total | 7,706 | 10,735 | 63 | 18,504 |

CPA-7:

This CPA is part of the Nepal Biogas Support Program-PoA. This CPA includes 18,392 digesters which were implemented between 05/04/2014 and 31/12/2014.Table below provides an overview of the digesters implemented under CPA.

| Region Size | Hill | Terai | Mountain or Remote Hill | Total |
| --- | --- | --- | --- | --- |
| 2 m3 | 22 | 1 |  | 23 |
| 4 m3 | 1,071 | 167 | 1 | 1,239 |
| 6 m3 | 7,849 | 8,554 | 64 | 16,467 |
| 8 m3 | 142 | 521 |  | 663 |
| Total | 9084 | 9,243 | 65 | 18,392 |

CPA-8:

This CPA is part of the Nepal Biogas Support Program-PoA. This CPA includes 19,445 digesters which were implemented between 01/01/2015 and 08/04/2016.Table below provides an overview of the digesters implemented under CPA.

| Region Size | Hill | Terai | Mountain or Remote Hill | Total |
| --- | --- | --- | --- | --- |
| 2 m3 | 26 | 1 | 0 | 27 |
| 4 m3 | 1365 | 187 | 18 | 1570 |
| 6 m3 | 6927 | 9842 | 203 | 16972 |
| 8 m3 | 223 | 650 | 3 | 876 |
| Total | 8541 | 10680 | 224 | 19445 |

CPA-9:

This CPA is part of the Nepal Biogas Support Program-PoA. This CPA includes 17,304 digesters which were implemented between 09/04/2016 and 12/07/2018. The table below provides the overview of digesters implemented under CPA.

| Region Size | Terai | Hill | Mountain or Remote Hill | Total |
| --- | --- | --- | --- | --- |
| 2 m3 | 3 | 3 | 0 | 6 |
| 4 m3 | 110 | 988 | 13 | 1111 |
| 6 m3 | 7713 | 7638 | 567 | 15918 |
| 8 m3 | 155 | 99 | 5 | 259 |
| 10 m3 | 8 | 2 | 0 | 10 |
| Total | 7989 | 8730 | 585 | 17304 |

CPA-10:

This CPA is part of the Nepal Biogas Support Program-Programme of Activity (PoA). This CPA includes 10,589 digesters which were implemented between 13/07/2018 and 19/10/2019. The table below provides the overview of digesters implemented under CPA-10.

| Region Size | Terai | Hill | Mountain or Remote Hill | Total |
| --- | --- | --- | --- | --- |
| 2 m3 | 2 | 4 | 0 | 6 |
| 4 m3 | 2215 | 1956 | 107 | 4278 |
| 6 m3 | 2111 | 4081 | 37 | 6229 |
| 8 m3 | 50 | 19 | 0 | 69 |
| 10 m3 | 2 | 5 | 0 | 7 |
| Total | 4380 | 6065 | 144 | 10589 |

B.1.1 Forward Action Requests

Not applicable

##### B.2. Post-Design Certification changes

Not Applicable

B.2.1. Temporary deviations from the approved Monitoring & Reporting Plan, methodology or standardized baseline

Not applicable

B.2.2. Corrections

Not applicable

B.2.3. Changes to start date of crediting period

No applicable

B.2.4. Permanent changes from the Design Certified monitoring plan, applied methodology or applied standardized baseline

Not applicable

B.2.5. Changes to project design of approved project

Not applicable

#### SECTION C. DESCRIPTION OF MONITORING SYSTEM APPLIED BY THE PROJECT

As a CME as well as CPA implementer, AEPC maintains the database of the biogas plants installed by the pre-qualified companies. On the behalf of AEPC, Biogas Sector Partnership Nepal (BSP-Nepal), a national level non-governmental organization keeps the database for the PoA. BSP-Nepal facilitates and provides technical assistance to biogas companies, processes the subsidy applications and recommend AEPC for subsidy reimbursement to the users through BCs. It also assists in conducting quality control and regular monitoring of the installed biogas digesters and developing skill enhancement among BCs. The Biogas User’s Survey is conducted every year as a basis for emission reduction calculation. The third party (consultant) conducts the Biogas User Survey. Based on the survey, AEPC prepares monitoring report and maintain all required documents for verification. The roles and responsibilities of each entity for GHG monitoring are shown below:

Alternative Energy Promotion Centre

- Data/Documentation Management

- Consultant Section for BUS

- Monitoring and quality assurance

- Act as CME

- Provide database to consultant and monitor BUS

- Prepare MR and report to the DOE

Consultant (Third Party)

- Sampling from given database

- Enumerators selection and orientation to them consulting with AEPC

- Conduct biogas user’s survey and prepare BUS report required for verification

- Submit the final BUS report to AEPC

Biogas Sector Partnership-Nepal

- Maintain database of biogas plants, if applicable and provide to AEPC

- Support AEPC in quality assurance, quality control, and regular monitoring of biogas plants.

#### SECTION D. DATA AND PARAMETERS

##### D.1. Data and parameters fixed ex ante or at renewal of crediting period

| Relevant SDG Indicator | 3.9.1 Mortality rate attributed to household and ambient air pollution |
| --- | --- |
| Data/parameter: | NCVbiomass |
| Unit | TJ/tone |
| Description | Net calorific value of the non-renewable biomass that is substituted |
| Source of data | IPCC guidelines. |
| Value(s) applied) | 0.015 (CP1) 0.0156 (CP2) |
| Choice of data or measurement methods and procedures | For Crediting Period 1 (CP1): AMS-I.E. Ver 4 requires using this value. For Crediting Period 2 (CP2): Methodology AMS I.E. Version 09 |
| Purpose of data | Emission reduction calculation |
| Additional comments | This value is kept up to date with the IPCC guidelines. |

| Relevant SDG Indicator | 13.1.1 Number of countries that have communicated the establishment or operationalization of an integrated policy/strategy/plan which increases their ability to adapt to the adverse impacts of climate change, and foster climate resilience and low greenhouse gas emissions development in a manner that does not threaten food production (including a national adaptation plan, nationally determined contribution, national communication, biennial update report or other) |
| --- | --- |
| Data/parameter: | EFprojected_fossil fuel |
| Unit | tCO2/TJ |
| Description | Emission factor for the projected fossil fuel consumption in the baseline. |
| Source of data | Approved small scale methodology AMS.I.E (version 4.0) |
| Value(s) applied) | 81.6 (CP1) 63.7 (CP2) |
| Choice of data or measurement methods and procedures | AMS-I.E. requires using this value. |
| Purpose of data | Emission reduction calculation |
| Additional comments | NA |

| Relevant SDG Indicator | 3.9.1 Mortality rate attributed to household and ambient air pollution |
| --- | --- |
| Data/parameter: | fNRB,y |
| Unit | % |
| Description | Fraction of biomass used in the absence of the project activity in year y that can be established as non-renewable biomass using nationally approved methods |
| Source of data | For CP1: "Default values of fraction of non-renewable biomass for Least Developed Countries and Small Island Developing States (version 01.0)" EB 67 Annex 22 For CP2: Calculated as per “TOOL30: Calculation of the fraction of non-renewable biomass version 02” |
| Value(s) applied) | 86% (CP1) 86.1% (CP2) |
| Choice of data or measurement methods and procedures | For CP 1 Default approved by the CDM EB as the value for the fraction of NRB in Nepal. For CP 2 The value is calculated as 86.1% using the national statistics and also validated by the Ministry of Forest and Environment, Government of Nepal. This value is for the national level and fixed ex-ante. |
| Purpose of data | Emission reduction calculation |
| Additional comments | EB 67 Annex 22 decision stipulates using this value |

| Relevant SDG Indicator | 7.1.2 Proportion of population with primary reliance on clean fuels and technology |
| --- | --- |
| Data/parameter: | Ns,r / |
| Unit | Numbers |
| Description | Number of digesters in each size category (in m3) and region (Terrai, Hill and, if available, Remote Hill or Mountain) implemented under the CPA |
| Source of data | CPA database |
| Value(s) applied) | CPA-2: 19,927 CPA-3: 19,959 CPA-4: 19,970 CPA-5: 19,842 CPA-6: 18,504 CPA-7: 18,392 CPA-8: 19,445 CPA-9: 17,304 |
| Choice of data or measurement methods and procedures | The registration procedure of the BSP database avoids double counting of digesters and the registration of digesters that have not been commissioned. The BSP database is the basis for subsidy disbursement. The data used to maintain this database is gathered according to defined procedures, making it a reliable source of information. |
| Purpose of data | Calculation of baseline emissions |
| Additional comments | Based on the size category of digester implementation between applicable vintage for each CPAs. Applicable to Crediting Period 1 |

| Relevant SDG Indicator | 7.1.2 Proportion of population with primary reliance on clean fuels and technology |
| --- | --- |
| Data/parameter: | NHH |
| Unit | Numbers |
| Description | Number of households in each CPA in year y |
| Source of data | BSP database |
| Value(s) applied) | CPA-1: 19,999 CPA-2: 19,927 CPA-3: 19,959 CPA-4: 19,970 CPA-5: 19,942 CPA-10: 10,589 |
| Choice of data or measurement methods and procedures | The registration procedure of the database avoids double counting of digesters and the registration of digesters that have not been commissioned. |
| Purpose of data | Calculation of baseline emission |
| Additional comments | During calculation of Emission Reduction, it will be based on actual number of households having the biogas operational Applicable to Crediting Period 2 |
| Relevant SDG Indicator | 3.9.1 Mortality rate attributed to household and ambient air pollution |
| Data/parameter: | QNRBrepl. |
| Unit | Tonne per year and appliance |
| Description | Quantity of woody biomass that is substituted or displaced in tonnes per year and appliance |
| Source of data | Calculated |
| Value(s) applied) | 3.33 |
| Choice of data or measurement methods and procedures | Calculated based on survey and historic data, such as Biogas User Survey (BUS). The BUS is based on survey techniques and has been confirmed in the context of registered CDM project 5416. |
| Purpose of data | Calculation of baseline emissions |
| Additional comments | To be re-assessed at renewal of crediting period of CPA. - As per paragraph 6 (a) of the methodology By represents the estimated average annual consumption of woody biomass per appliance (tonnes/year) derived from surveys or historic information. - As per SSC WG clarification SSC 543 the estimate can be fixed ex ante- Applicable to Crediting Period 1 |

| Relevant SDG Indicator | 3.9.1 Mortality rate attributed to household and ambient air pollution |
| --- | --- |
| Data/parameter: | BCPJ,HH,y |
| Unit | tonnes/household/year |
| Description | Average annual consumption of woody biomass per household in the pre-project devices during the project activity, if it is found that pre-project devices were not completely displaced but continue to be used to some extent. |
| Measured/calculated/default | Calculated |
| Source of data | Biogas User Survey |
| Value(s) of monitored parameter | CPA-1: 0.51 CPA-2: 0.47 CPA-3: 0.50 CPA-4: 0.48 CPA-5: 0.48 CPA-10: 0.51 |
| Monitoring equipment | Survey |
| Measuring/reading/recording frequency: | At least once every two years (biennial) |
| Calculation method (if applicable): | Biogas User Survey was conducted on a sample of households. The sample size was determined to achieve 90% confidence interval and a 10% margin of error. During the survey, the estimates of the biogas users on the average annual consumption of woody biomass during the monitoring period was captured and weighted average for all the strata and sizes has been calculated |
| QA/QC procedures: | Though the methodology requires sample survey biennial, PP conducts the user survey annually to ensure the number of biogas digesters operational for that particular year for CPA and the consumption of the woody biomass by pre-project device if any during the project activities. |
| Purpose of data: | Calculation of baseline emission |
| Additional comments: | ERs was accounted only for functional biogas in the particular monitoring period Applicable to Crediting Period 2 |

| Relevant SDG Indicator | 3.9.1 Mortality rate attributed to household and ambient air pollution |
| --- | --- |
| Data/parameter: | By |
| Unit | tonnes/household/year |
| Description | Quantity of woody biomass that is substituted or displaced |
| Measured/calculated/default | Calculated |
| Source of data | Biogas User Survey |
| Value(s) of monitored parameter | CPA-1: 75,737.81 tonnes CPA-2: 51,322.37 tonnes CPA-3: 55,250.57 tonnes CPA-4: 54,105.41 tonnes CPA-5: 29,915.13 tonnes CPA-10: 39,391.46 tonnes |
| Monitoring equipment | Survey |
| Measuring/reading/recording frequency: | Once in a year |
| Calculation method (if applicable): | The calculation of the By depends on the operational status of the biogas units for the particular monitoring period and the operational status will be checked annually during the Biogas User Survey. From the total population of biogas units included in the project activity, statistically representative samples will be drawn for the purpose of carrying out the survey. The sample size is determined to achieve 90% confidence interval and a 10% margin of error. The percentage of biogas units found to be operational during the sample survey shall be used to calculate the weighted average operational status of the biogas which then will be used to calculate By as follows: By = NHH * (BCBL,HH,y – BCPJ,HH,y) NHH = N * PY, where N is the number of bio digesters installed in the project and PY is Proportion of Bio digesters operational estimated based on the sample survey |
| QA/QC procedures: | Though the methodology requires sample survey biannually, PP conducts the user survey annually to ensure the number of biogas digesters operational for that particular year for each CPA |
| Purpose of data: | Calculation of baseline emission |
| Additional comments: | Once the biogas included in the component project activity completes its operational lifetime, those biogas will not be considered for the next consecutive monitoring. Applicable to Crediting Period 2 |

##### D.2 Data and parameters monitored

| Relevant SDG Indicator | 7.1.2 Proportion of population with primary reliance on clean fuels and technology |
| --- | --- |
| Data/parameter: | P |
| Unit | % |
| Description | The share of digesters operational |
| Measured/calculated/default | Calculated |
| Source of data | Biogas User Survey 2020/21 for all CPAs |
| Value(s) of monitored parameter | CPA 1: 83.60% CPA-2: 86.43% CPA-3: 93.51% CPA-4: 91.12% CPA-5: 93.55% CPA-6: 87.42% CPA-7: 83.19% CPA-8: 91.67% CPA-9: 94.11% CPA 10: 82.12% |
| Monitoring equipment | Survey |
| Measuring/reading/recording frequency: | Biennial |
| Calculation method (if applicable): | Ratio calculated as number of digesters found to be operating from the total number of digesters surveyed |
| QA/QC procedures: | The Internal Quality Control system samples 5% of the digesters that are newly implemented, 2.5% of the digesters that are two year in operation and 2.5% of the digesters that have been operational for three years as part of the Internal Quality Control System. For the purpose of the current monitoring period, Biogas Users’ Survey has been taken as the means to check the operational status of the biogas digester as the user survey gives the up-to-date value. The reliability check is done for each CPA in the BUS survey reports and the margin of error less than 10%. |
| Purpose of data: | ER calculation |
| Additional comments: | Requirements as defined in the sampling plan is met. |

| Relevant SDG Indicator | 3.9.1 Mortality rate attributed to household and ambient air pollution |
| --- | --- |
| Data/parameter: | Users’ perception on reduction in indoor air pollution |
| Unit | Qualitative |
| Description | Users’ perception on reduction in indoor air pollution |
| Measured/calculated/default | Calculated |
| Source of data | Biogas User Survey 2020/21 for all CPAs |
| Value(s) of monitored parameter | CPA-1: 97.61% CPA-2: 100% CPA-3: 97.77% CPA-4: 93.26% CPA-5: 98.90% CPA-6: 97.70% CPA-7: 96.43% CPA-8: 100% CPA-9: 98.93% CPA-10: 100% |
| Monitoring equipment | Survey |
| Measuring/reading/recording frequency: | at least biennial |
| Calculation method (if applicable): | Calculated as % of users perceived the reduction (Reduce and drastically reduce) in indoor air pollution due to the biogas implementation |
| QA/QC procedures: | The selection of households under the surveys ensures that the percentages of household in different strata are met for each individual CPA included in the PoA; survey tried to capture the view of the women actually involved in cooking. |
| Purpose of data: | Sustainable Development Assessment. |
| Additional comments: | Requirements as defined in the sampling plan shall be met. |

| Relevant SDG Indicator | 3.9.1 Mortality rate attributed to household and ambient air pollution |
| --- | --- |
| Data/parameter: | Reduction in health problem |
| Unit | Qualitative |
| Description | Users’ perception on reduction in health problem |
| Measured/calculated/default | Calculated |
| Source of data | Biogas User Survey 2020/21 for all CPAs |
| Value(s) of monitored parameter | CPAs; % HH perceived reduction in. Eye infection; Respiratory diseases; Cough; Fire related injury. CPA-1; 94.05; 89.29; 86.90; 91.67. CPA-2; 100; 93.02; 94.19; 93.02. CPA-3; 98.92; 90.32; 89.25; 93.55. CPA-4; 91.09; 97.64; 77.53; 83.15. CPA-5; 97.80; 93.41; 90.11; 100. CPA-6; 95.40; 95.40; 78.16; 85.06. CPA-7; 95.24; 88.10; 88.10; 88.10. CPA-8; 98.90; 98.90; 92.31; 95.60. CPA-9; 97.80; 88.30; 88.30; 88.30. CPA-10; 95.51; 91.01; 94.38; 96.63. |
| Monitoring equipment | Survey |
| Measuring/reading/recording frequency: | at least biennial |
| Calculation method (if applicable): | Calculated as % of users perceived the reduction of different health problem caused by indoor air pollution after installation of biogas. |
| QA/QC procedures: | The selection of households under the surveys ensures that the percentages of household in different strata are met for each individual CPA included in the PoA |
| Purpose of data: | Sustainable Development Assessment. |
| Additional comments: | Requirements as defined in the sampling plan is met. |

| Relevant SDG Indicator | 3.9.1 Mortality rate attributed to household and ambient air pollution |
| --- | --- |
| Data/parameter: | User’s perception in Time saving for the cooking (reduce exposure to indoor air pollution) |
| Unit | Qualitative |
| Description | Users’ perception on time saving for cooking due to project. |
| Measured/calculated/default | Calculated |
| Source of data | Biogas User Survey 2020/21 for all CPAs |
| Value(s) of monitored parameter | CPAs; % HH perceived reduction in cooking time for. Men; Women; Children. CPA-1; 40.48; 98.81; 17.86. CPA-2; 48.84; 100; 27.91. CPA-3; 25.81; 96.77; 21.51. CPA-4; 46.07; 97.75; 16.85. CPA-5; 36.26; 100; 29.67. CPA-6; 42.86; 100; 17.86. CPA-7; 38.10; 100; 25. CPA-8; 30.77; 100; 23.08. CPA-9; 51.06; 100; 19.15. CPA-10; 39.33; 100; 5.62. |
| Monitoring equipment | Survey |
| Measuring/reading/recording frequency: | At least biennial |
| Calculation method (if applicable): | Calculated as % of users perceived the reduction in cooking time for men, women and children after installation of biogas. |
| QA/QC procedures: | The selection of households under the surveys ensures that the percentages of household in different strata are met for each individual CPA included in the PoA |
| Purpose of data: | Sustainable Development Assessment. |
| Additional comments: | Requirements as defined in the sampling plan is met. |

| Relevant SDG Indicator | 7.1.2 Proportion of population with primary reliance on clean fuels and technology |
| --- | --- |
| Data/parameter: | Time saving (Fuel wood collection) |
| Unit | Qualitative |
| Description | Users’ perception on time saving due to project for firewood collection |
| Measured/calculated/default | Calculated |
| Source of data | Biogas User Survey 2020/21 for all CPAs |
| Value(s) of monitored parameter | CPAs; % HH perceived reduction in firewood collection time for. Men; Women; Children. CPA-1; 73.81; 95.24; 10.71. CPA-2; 65.12; 98.84; 29.07. CPA-3; 49.46; 97.85; 18.28. CPA-4; 65.17; 98.88; 15.73. CPA-5; 73.63; 100; 17.58. CPA-6; 83.93; 100; 14.29. CPA-7; 63.10; 100; 26.19. CPA-8; 62.64; 98.90; 7.69. CPA-9; 70.21; 100; 19.15. CPA-10; 49.44; 98.88; 5.62. |
| Monitoring equipment | Survey |
| Measuring/reading/recording frequency: | At least biennial |
| Calculation method (if applicable): | Calculated as % of users perceived the reduction in cooking time for men, women and children after installation of biogas. |
| QA/QC procedures: | The selection of households under the surveys ensures that the percentages of household in different strata are met for each individual CPA included in the PoA |
| Purpose of data: | Sustainable Development Assessment. |
| Additional comments: | Requirements as defined in the sampling plan is met. |

| Relevant SDG Indicator | 3.9.3 Mortality rate attributed to unintentional poisoning |
| --- | --- |
| Data/parameter: | Users perception in reduction of chemical fertilizers |
| Unit | Qualitative |
| Description | Users’ perception on reduction in use of chemical fertilizers and use of bio-slurry |
| Measured/calculated/default | Calculated |
| Source of data | Biogas User Survey 2020/21 for all CPAs |
| Value(s) of monitored parameter | CPAs; % changes in use of chemical fertilizers and increase in use of bio-slurry. Farm Yard Manure; Bio-slurry; Urea; DAP; Potash. CPA-1; 32.41; 100; 33.10; 40.93; 58.06. CPA-2; 28.68; 100; 38.54; 0; 50. CPA-3; 31.47; 100; 27.27; 29.35; 41.18. CPA-4; 30.62; 100; 37.42; 0; 58.62. CPA-5; 32.09; 100; 41.51; 35.74; 33.26. CPA-6; 30.65; 100; 35.52; 36.65; 46.43. CPA-7; 27.25; 100; 37.99; 39.33; 51.23. CPA-8; 28.59; 100; 25.66; 28.23; 33.33. CPA-9; 33.13; 100; 39.12; 42.38; 56.08. CPA-10; 32.59; 100; 31.36; 50; 0. |
| Monitoring equipment | Survey |
| Measuring/reading/recording frequency: | at least biennial |
| Calculation method (if applicable): | Calculated as % use of the Bio-slurry and chemical fertilizers before and after biogas installation which is perceived by biogas users. |
| QA/QC procedures: | The selection of households under the surveys ensures that the percentages of household in different strata are met for each individual CPA included in the PoA |
| Purpose of data: | Sustainable Development Assessment. |
| Additional comments: | Requirements as defined in the sampling plan is met. |

| Relevant SDG Indicator | 3.9.2 Mortality rate attributed to unsafe water, unsafe sanitation and lack of hygiene (exposure to unsafe Water, Sanitation and Hygiene for All (WASH) services) |
| --- | --- |
| Data/parameter: | Improved access to sanitation services |
| Unit | Number |
| Description | Users’ perception on connection of toilet to biogas |
| Measured/calculated/default | Calculated |
| Source of data | Biogas User Survey 2020/21 for all CPAs |
| Value(s) of monitored parameter | CPA-1: 67.86% CPA-2: 74.42% CPA-3: 63.44% CPA-4: 89.89% CPA-5: 85.71% CPA-6: 87.36% CPA-7: 79.76% CPA-8: 85.71% CPA-9: 79.79% CPA-10: 96.63% |
| Monitoring equipment | Survey |
| Measuring/reading/recording frequency: | at least biennial |
| Calculation method (if applicable): | Calculated as % of households connected the toilet to the biogas. |
| QA/QC procedures: | The selection of households under the surveys ensures that the percentages of household in different strata are met for each individual CPA included in the PoA |
| Purpose of data: | Sustainable Development Assessment. |
| Additional comments: | Requirements as defined in the sampling plan is met. |

| Relevant SDG Indicator | 7.1.2 Proportion of population with primary reliance on clean fuels and technology |
| --- | --- |
| Data/parameter: | Trainings to Masons |
| Unit | Number of people trained to promote Biogas plants |
| Description | Masons involved in constructing the biogas plants shall receive training on the proper installation of biogas digesters. |
| Measured/calculated/default | default |
| Source of data | Training Reports |
| Value(s) of monitored parameter | Since, all the biogas digesters are already implemented in all CPAs, the monitoring of the training to the masons who constructed the digesters for CPAs are not applicable for monitoring of the CPAs. But the training to the mason is provided by AEPC/respective biogas companies etc to the biogas technician as and when required. During this monitoring period, the training could not be conducted due to COVID but Two Mason (Biogas Technician Level-1) Training was conducted for 75 to maintain the sufficient manpower in the market that will help in promoting biogas technology in last monitoring period. |
| Monitoring equipment | Training Report |
| Measuring/reading/recording frequency: | at least biennial |
| Calculation method (if applicable): | Number of masons trained during the monitoring period. |
| QA/QC procedures: | N/A |
| Purpose of data: | Sustainable Development Assessment. |
| Additional comments: | Requirements as defined in the sampling plan is met. |

| Relevant SDG Indicator | Safeguarding Principle 4.3.8 |
| --- | --- |
| Data/parameter: | Impact on Crop Productivity |
| Unit | Qualitative |
| Description | Users’ perception on Impact on crop productivity |
| Measured/calculated/default | calculated |
| Source of data | Biogas User Survey 2020/21 for all CPAs |
| Value(s) of monitored parameter | % users perceived in increase in productivity due to bio-slurry use from Biogas: CPA-1: 65.43 % CPA-2: 74.12 % CPA-3: 83.15 % CPA-4: 67.05 % CPA-5: 73.49 % CPA-6: 83.95 % CPA-7: 90.24% CPA-8: 78.16% CPA-9: 85.56% CPA-10: 84.09 % |
| Monitoring equipment | Survey |
| Measuring/reading/recording frequency: | at least biennial |
| Calculation method (if applicable): | Calculated as percentage of users perceived the increment in productivity by the use of bio-slurry from biogas |
| QA/QC procedures: | The selection of households under the surveys ensures that the percentages of household in different strata are met for each individual CPA included in the PoA |
| Purpose of data: | Sustainable Development Assessment. |
| Additional comments: | Requirements as defined in the sampling plan is met. |

##### D.3. Comparison of monitored parameters with last monitoring period

| Data/Parameter | Value obtained in this monitoring period | Value obtained last monitoring period |
| --- | --- | --- |
| P | CPA-1: 83.60% CPA-2: 86.43% CPA-3: 93.51% CPA-4: 91.12% CPA-5: 93.55% CPA-6: 87.42% CPA-7: 83.19% CPA-8: 91.67% CPA-9: 94.11% CPA-10: 82.12% | CPA-1: 86.18 % CPA-2: 88.26 % CPA-3: 84.34 % CPA-4: 84.68 % CPA-5: 86.63 % CPA-6: 86.13 % CPA-7: 92.71 % CPA-8: 82.64 % CPA-9: 93.86 % CPA-10: 83.53% |
| Users’ perception on reduction in indoor air pollution | CPA-1: 97.61% CPA-2: 100% CPA-3: 97.77% CPA-4: 93.26% CPA-5: 98.90% CPA-6: 97.70% CPA-7: 96.43% CPA-8: 100% CPA-9: 98.93% CPA-10: 100% | CPA-1: 98% CPA-2: 96% CPA-3: 99% CPA-4: 100% CPA-5: 100% CPA-6: 96% CPA-7: 100% CPA-8: 100% CPA-9: 97% CPA-10: 100% |
| Reduction in health problem | CPAs; % HH perceived reduction in. Eye Infection; RD; Cough; Fire Related Injury. CPA-1; 94.05; 89.29; 86.90; 91.67. CPA-2; 100; 93.02; 94.19; 93.02. CPA-3; 98.92; 90.32; 89.25; 93.55. CPA-4; 91.09; 97.64; 77.53; 83.15. CPA-5; 97.80; 93.41; 90.11; 100. CPA-6; 95.40; 95.40; 78.16; 85.06. CPA-7; 95.24; 88.10; 88.10; 88.10. CPA-8; 98.90; 98.90; 92.31; 95.60. CPA-9; 97.80; 88.30; 88.30; 88.30. CPA-10; 95.51; 91.01; 94.38; 96.63. | CPAs; % HH perceived reduction in. Eye Infection; RD; Cough; Fire Related Injury. CPA-1; 90; 86; 80; 85. CPA-2; 96; 93; 86; 95. CPA-3; 100; 99; 99; 99. CPA-4; 99; 99; 97; 97. CPA-5; 99; 96; 94; 96. CPA-6; 99; 99; 89; 87. CPA-7; 93; 87; 95; 88. CPA-8; 97; 97; 97; 97. CPA-9; 92; 96; 92; 92. CPA-10; 97; 97; 97; 97. |
| User’s perception in Time saving for the cooking (reduce exposure to indoor air pollution) | CPAs; % HH perceived reduction in cooking time for. Men; Women; Children. CPA-1; 40.48; 98.81; 17.86. CPA-2; 48.84; 100; 27.91. CPA-3; 25.81; 96.77; 21.51. CPA-4; 46.07; 97.75; 16.85. CPA-5; 36.26; 100; 29.67. CPA-6; 42.86; 100; 17.86. CPA-7; 38.10; 100; 25. CPA-8; 30.77; 100; 23.08. CPA-9; 51.06; 100; 19.15. CPA-10; 39.33; 100; 5.62. | CPAs; % HH perceived reduction in cooking time for. Men; Women; Children. CPA-1; 17; 99; 7. CPA-2; 4; 100; 4. CPA-3; 24; 100; 14. CPA-4; 25; 97; 7. CPA-5; 32; 96; 23. CPA-6; 24; 97; 4. CPA-7; 7; 95; 8. CPA-8; 12; 99; 6. CPA-9; 25; 99; 4. CPA-10; 11; 99; 10. |
| Time saving (Fuel wood collection) | CPAs; % HH perceived reduction in firewood collection time for. Men; Women; Children. CPA-1; 73.81; 95.24; 10.71. CPA-2; 65.12; 98.84; 29.07. CPA-3; 49.46; 97.85; 18.28. CPA-4; 65.17; 98.88; 15.73. CPA-5; 73.63; 100; 17.58. CPA-6; 83.93; 100; 14.29. CPA-7; 63.10; 100; 26.19. CPA-8; 62.64; 98.90; 7.69. CPA-9; 70.21; 100; 19.15. CPA-10; 49.44; 98.88; 5.62. | CPAs; % HH perceived reduction in firewood collection time for. Men; Women; Children. CPA-1; 45; 98; 7. CPA-2; 51; 92; 0. CPA-3; 44; 94; 10. CPA-4; 61; 100; 4. CPA-5; 65; 96; 1. CPA-6; 67; 96; 1. CPA-7; 53; 97; 20. CPA-8; 60; 99; 6. CPA-9; 62; 96; 1. CPA-10; 56; 99; 7. |
| Users perception in reduction of chemical fertilizers | CPAs; % changes in use of chemical fertilizers and increase in use of bio-slurry. FYM; Bio-slurry; Urea; DAP; Potash. CPA-1; 32.41; 100; 33.10; 40.93; 58.06. CPA-2; 28.68; 100; 38.54; 0; 50. CPA-3; 31.47; 100; 27.27; 29.35; 41.18. CPA-4; 30.62; 100; 37.42; 0; 58.62. CPA-5; 32.09; 100; 41.51; 35.74; 33.26. CPA-6; 30.65; 100; 35.52; 36.65; 46.43. CPA-7; 27.25; 100; 37.99; 39.33; 51.23. CPA-8; 28.59; 100; 25.66; 28.23; 33.33. CPA-9; 33.13; 100; 39.12; 42.38; 56.08. CPA-10; 32.59; 100; 31.36; 50; 0. | CPAs; % changes in use of chemical fertilizers and increase in use of bio-slurry. FYM; Bio-slurry; Urea; DAP; Potash. CPA-1; 35; 100; 38; 26; 0. CPA-2; 23; 100; 46; 22; 45. CPA-3; 23; 100; 28; 27; 27. CPA-4; 23; 100; 43; 25. CPA-5; 39; 100; 37; 2; 50. CPA-6; 24; 100; 29; 12; 4. CPA-7; 40; 100; 42; 36; 33. CPA-8; 27; 100; 13; 6; 36. CPA-9; 29; 100; 55; 27; 33. CPA-10; 27; 100; 14; 6; 36. |
| Improved access to sanitation services | CPA-1: 67.86 % CPA-2: 74.42% CPA-3: 63.44% CPA-4: 89.89% CPA-5: 85.71% CPA-6: 87.36% CPA-7: 79.76% CPA-8: 85.71% CPA-9: 79.79% CPA-10: 96.63 % | CPA-1: 84 % CPA-2: 71% CPA-3: 70% CPA-4: 97% CPA-5: 70% CPA-6: 83% CPA-7: 93% CPA-8: 96% CPA-9: 84% CPA-10: 92% |
| Trainings to Masons | Not applicable (Not conducted due to CoVID) but 75 were trained in last MP | Not applicable (Not conducted due to CoVID) but 75 were trained in last MP |
| Impact on Crop Productivity | CPA-1: 65.43% CPA-2: 74.12 % CPA-3: 83.15 % CPA-4: 67.05 % CPA-5: 73.49 % CPA-6: 83.95 % CPA-7: 90.24% CPA-8: 78.16% CPA-9: 85.56% CPA-10: 84.09 % | CPA-1: 80% CPA-2: 80 % CPA-3: 89 % CPA-4: 72 % CPA-5: 82 % CPA-6: 83 % CPA-7: 89% CPA-8: 78% CPA-9: 79% CPA-10: 78% |

##### D.4. Implementation of sampling plan

Since the monitoring parameters for all CPAs implemented under the PoA are same, the CME adopts a common monitoring framework for all the specific case CPAs implemented under the PoA. Annual monitoring was conducted through the biogas users’ surveys where the following parameters were monitored as stipulated in the section E.7.2 of the registered PoA-DD and the specific VPA-DDs and the transition documents.

- Digester performance

- Displacement of Non renewable biomass

- Other Socio-economic Parameters stipulated in CPA-DD for SDG monitoring

The coordinating/managing entity opted for a monitoring system where each CPA within the PoA is monitored (Please refer to section C of the CDM PoA DD). The monitoring parameter stipulated in the PoA DD is the “digester performance”. In order to monitor this parameter, CME commissioned an independent consultant through a competitive bidding process. The consultant, aligning with the monitoring requirements of the PoA estimated the sample required for the monitoring, drafted the questionnaires and mobilized the team for on-site survey. Having accumulated the information from the on-site survey, the consultant team prepared the reports for each CPA and submitted the same to the AEPC.

### Sample Size Determination

Sample size was determined using stratified random sampling consistent with the monitoring plan of the registered PoA-DD and respective CPA-DDs and for sampling and surveys for CDM project activities and programme of activities and as specified in the registered PoA-DD. The sampling was performed within the level of precision of 10% and a confidence level of 90%.

The sample size calculation was carried out using formula as provided in the guidelines.

n≥1.6452NVN-1×0.12+1.6452V ------------------------------------------------  1

Where,

V=SD2p2, -------------------------  2

SD2 is the overall variance and

p2    is the overall proportion.

SD2=ga×pa1-pa+gb×pb1-pb+……gk×pk1-pkN ------------------------- eq. 3

p2=(ga×pa)+(gb×pb)+….(gk×pk)N

------------------------- eq. 4

Where,

| Symbol | Description | CPA-1 | CPA-2 | CPA-3 | CPA-4 | CPA-5 | CPA-6 | CPA-7 | CPA-8 | CPA-9 | CPA-10 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| g1 | total number of plants in Remote Hill | 105 | 144 | 161 | 123 | 229 | 63 | 65 | 224 | 585 | 144 |
| p1 | Expected Proportion of operational plants in Remote Hill in 2020/21 (based on BUS 2019/20) | 1.0 | 0 | 1.0 | 0.0 | 0.0 | 0 | 0.0 | 1.0 | 1 | 1.0 |
| g2 | total number of plants in Hill | 8939 | 9437 | 10754 | 10720 | 9669 | 7706 | 9084 | 8541 | 8730 | 6065 |
| p2 | Expected Proportion of operational plants in Hill in 2020/21(based on BUS 2019/20) | 0.9318 | 0.8421 | 0.8864 | 0.8182 | 0.8718 | 0.8529 | 0.9268 | 0.8889 | 0.9024 | 0.8776 |
| g3 | total number of plants in Terai | 10955 | 10346 | 9044 | 9127 | 9944 | 10735 | 9243 | 10,680 | 7989 | 4380 |
| p3 | Expected Proportion of operational plants in Terai in 2020/21 (based on BUS 2019/20) | 0.8148 | 0.9318 | 0.7895 | 0.8919 | 0.8810 | 0.8723 | 0.9268 | 0.7727 | 0.9737 | 0.7714 |
| N | total number of plants under specific CPA | 19999 | 19927 | 19959 | 19970 | 19842 | 18504 | 18392 | 19445 | 17304 | 10589 |
| n | required sample size for each CPA | 41 | 36 | 51 | 49 | 41 | 44 | 24 | 57 | 20 | 53 |
| n | Actual number of samples taken for sampling | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 |

The sample size has been calculated as per the annex 4 of the registered PoA-DD. The registered PDD for PoA has retained 72 sample households for monitoring during annual surveys. However, the sample size for the CPAs of the PoA is dependent on “p”, the proportion of biogas digester expected to be operational. The change in value of “p” therefore changes the total sample size required. Based on the observed operational status of biogas plants in remote hills, hills and Terai, in the previous biogas user survey for each CPA, the expected ‘p’ value has been applied and required sample size has been calculated. Further, in order to avoid any low response rate and answers bias, the sample size has been enlarged. For the purpose of current monitoring period, the CME used a higher sample size instead of the required minimum and accordingly the survey agency conducted the survey to arrive at the results as presented. The sample size calculation is presented in the CER calculation sheets.

### Allocation of samples

As stratified sampling has been used, minimum sample required for the Terai, Hill and Remote hill have been met. The tables below depict the sample allocation against the installed digesters in respective CPAs.

CPA-1

| Ecological Belts | Installed Biogas Plants |  | Sample Required | Sample Biogas Plants |
| --- | --- | --- | --- | --- |
|  | Number | Proportion |  | Number |
| Remote Hill | 105 | 0.52 | 1 | 4 |
| Hill | 8939 | 44.70 | 18 | 44 |
| Terai | 10955 | 54.78 | 22 | 52 |
| Total | 19999 | 100 | 41 | 100 |

CPA-2

| Ecological Belts | Installed Biogas Plants |  | Sample Required | Sample Biogas Plants |
| --- | --- | --- | --- | --- |
|  | Number | Proportion |  | Number |
| Remote Hill | 144 | 0.72 | 1.0 | 4 |
| Hill | 9437 | 47.36 | 27.0 | 46 |
| Terai | 10346 | 51.92 | 30.0 | 50 |
| Total | 19927 | 100 | 58 | 100 |

CPA-3

| Ecological Belts | Installed Biogas Plants |  | Sample Required | Sample Biogas Plants |
| --- | --- | --- | --- | --- |
|  | Number | Proportion |  | Number |
| Remote Hill | 161 | 0.81 | 1.0 | 4 |
| Hill | 10754 | 53.88 | 31.0 | 51 |
| Terai | 9044 | 45.31 | 26.0 | 45 |
| Total | 19,959 | 100 | 58 | 100 |

CPA-4

| Ecological Belts | Installed Biogas Plants |  | Sample Required | Sample Biogas Plants |
| --- | --- | --- | --- | --- |
|  | Number | Proportion |  | Number |
| Remote Hill | 123 | 0.62 | 1.0 | 4 |
| Hill | 10720 | 53.68 | 31.0 | 51 |
| Terai | 9127 | 45.70 | 26.0 | 45 |
| Total | 19,970 | 100 | 58 | 100 |

CPA-5

| Ecological Belts | Installed Biogas Plants |  | Sample Required | Sample Biogas Plants |
| --- | --- | --- | --- | --- |
|  | Number | Proportion |  | Number |
| Remote Hill | 229 | 1.15 | 1.0 | 4 |
| Hill | 9669 | 48.73 | 28.0 | 46 |
| Terai | 9944 | 50.12 | 29.0 | 50 |
| Total | 19,842 | 100 | 58 | 100 |

CPA-6

| Ecological Belts | Installed Biogas Plants |  | Sample Required | Sample Biogas Plants |
| --- | --- | --- | --- | --- |
|  | Number | Proportion |  | Number |
| Remote Hill | 63 | 0.34 | 1.0 | 4 |
| Hill | 7706 | 41.65 | 24.0 | 40 |
| Terai | 10735 | 58.01 | 33.0 | 56 |
| Total | 18504 | 100 | 58 | 100 |

CPA-7

| Ecological Belts | Installed Biogas Plants |  | Sample Required | Sample Biogas Plants |
| --- | --- | --- | --- | --- |
|  | Number | Proportion |  | Number |
| Remote Hill | 65 | 0.35 | 1.0 | 4 |
| Hill | 9084 | 49.39 | 28.0 | 47 |
| Terai | 9243 | 50.26 | 29.0 | 49 |
| Total | 18392 | 100 | 58 | 100 |

CPA-8

| Ecological Belts | Installed Biogas Plants |  | Sample Required | Sample Biogas Plants |
| --- | --- | --- | --- | --- |
|  | Number | Proportion |  | Number |
| Remote Hill | 224 | 1.15 | 1 | 4 |
| Hill | 8541 | 43.92 | 25 | 47 |
| Terai | 10680 | 54.92 | 31 | 49 |
| Total | 19445 | 100 | 57 | 100 |

CPA-9

| Ecological Belts | Installed Biogas Plants |  | Sample Required | Sample Biogas Plants |
| --- | --- | --- | --- | --- |
|  | Number | Proportion |  | Number |
| Remote Hill | 585 | 3.38 | 2.0 | 4 |
| Hill | 8730 | 50.45 | 28.0 | 50 |
| Terai | 7989 | 46.17 | 26.0 | 46 |
| Total | 17304 | 100 | 56 | 100 |

CPA-10

| Ecological Belts | Installed Biogas Plants |  | Sample Required | Sample Biogas Plants |
| --- | --- | --- | --- | --- |
|  | Number | Proportion |  | Number |
| Remote Hill | 144 | 1.36 | 2 | 4 |
| Hill | 6065 | 57.28 | 49 | 61 |
| Terai | 4380 | 41.36 | 35 | 45 |
| Total | 10589 | 100 | 86 | 110 |

### Survey

Sample households were selected accordingly using “Rand” function in Excel. Survey of those households were conducted in March/April 2021 in its regular monitoring schedule. The enumerators were trained on structured questionnaire. Having accumulated the data collected during the survey, the consultant analyzed the data using appropriate tools and prepared the “Biogas User Survey” report for individual CPAs.

The results from the monitoring for the operational status of the CPAs are given below:

| Particulars | CPA-1 | CPA-2 | CPA-3 | CPA-4 | CPA-5 | CPA-6 | CPA-7 | CPA-8 | CPA-9 | CPA-10 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| No of Plants in Remote Hill | 105 | 144 | 161 | 123 | 229 | 63 | 65 | 224 | 585 | 144 |
| Sample Taken in Remote Hill | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |
| Operational Status of sample in Remote Hill | 1.0000 | 0.7500 | 0.7500 | 0.2500 | 0.0000 | 0.7500 | 1.0000 | 0.7500 | 0.7500 | 0.2500 |
| No of Plants in Hill | 8939 | 9437 | 10754 | 10720 | 9669 | 7706 | 9084 | 8541 | 8730 | 6065 |
| Sample Taken in Hill | 44 | 46 | 51 | 51 | 46 | 40 | 47 | 44 | 50 | 61 |
| Operational Status of Sample in Hill | 0.7273 | 0.7391 | 0.9020 | 0.8431 | 0.8913 | 0.7000 | 0.6596 | 0.8409 | 0.9000 | 0.7377 |
| No of Plants in Terai | 10955 | 10346 | 9044 | 9127 | 9944 | 10735 | 9243 | 10680 | 7989 | 4380 |
| Sample Taken in Terai | 52 | 50 | 45 | 45 | 50 | 56 | 49 | 52 | 46 | 45 |
| Operational status in Terai | 0.9231 | 0.9800 | 0.9778 | 1.0000 | 1.0000 | 1.0000 | 1.0000 | 0.9808 | 1.0000 | 0.9556 |
| Total no of Biogas Plants installed | 19999 | 19927 | 19959 | 19970 | 19842 | 18504 | 18392 | 19445 | 17304 | 10589 |
| Weighted average operational status of CPA (Population) | 83.60% | 86.43% | 93.51% | 91.12% | 93.55% | 87.42% | 83.19% | 91.67% | 94.11% | 82.12% |

### Quality Assurance/Quality Control

Efforts were made to ensure the quality of the data collected from the field. QA/QC measures were implemented to attain the desired 90/10 confidence/precision for the parameters under consideration. The calculated precision of survey data for the operational status and the consumption of woody biomass after the project activities are less than the assumed precision (10%). This means the survey data comply with given precision. In order to assure the quality of data collected, the questionnaires were pre-tested prior to their introduction in the field. The reliability of the survey data were also checked by calculating the relative precision. The relative precision for “Average annual consumption of woody biomass per household in the pre-project devices during the project activity (Mean value parameter)” and “Digester performance (Operational %), a proportion parameter)  are shown in table below

| Particulars | CPA-1 | CPA-2 | CPA-3 | CPA-4 | CPA-5 | CPA-6 | CPA-7 | CPA-8 | CPA-9 | CPA-10 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Precision Calculated (Mean value Parameters)-% | 4.32 | 4.27 | 3.44 | 3.64 | 5.08 | 5.29 | 4.22 | 4.87 | 4.87 | 3.39 |
| Precision Calculated (Proportional Parameters)-% | 7.11 | 6.15 | 4.32 | 4.93 | 3.92 | 5.66 | 6.73 | 4.74 | 3.94 | 6.93 |
| Maximum Precision as per PoA-DD -% | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 |
| Precision Achieved | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes |

The aforementioned table precision test shows that the reliability of the survey data has been met.

#### SECTION E. CALCULATION OF SDG IMPACTS

##### E.1. Calculation of baseline value or estimation of baseline situation of each SDG Impact

For Crediting Period 1 (CP1):

Baseline Estimate for SDG 13

According to AMS-I.E. version 04, para 04, the emission reductions under a CPA are calculated as the following:

| In which: |  |  |
| --- | --- | --- |
| ERy | Emissions Reductions during the year y (tCO2e) |  |
| By | Quantity of woody biomass that is substituted or displaced in tonnes |  |
| fNRB.y | Default value of fraction of non-renewable biomass for Nepal, (86% fixed ex-ante) |  |
| NCVbiomass | Net calorific value of the non-renewable woody biomass that is substituted (IPCC default for wood fuel, 0.015 TJ/tonne. (Updated IPCC value) |  |
| EFprojected.fossilfuel | Emission factor for substitution of non-renewable woody biomass by similar consumers. Use a value of 81.6 tCO2/TJ. (Fixed Ex-ante) |  |

Following option a) of paragraph 6, By is “calculated as the product of the number of appliances multiplied by the estimate of average annual consumption of woody biomass per appliance (tonnes/year)”.

In the case of the present CPA, “the number of appliances” as deducted from the internal records (commissioning report/database) is corrected with the share of digesters actually in operation.

The “average annual consumption of woody biomass per appliance (tonnes/year)” is the biomass substituted or displaced, which is fixed ex- ante at 3.33 tonnes/year per appliance.

Thus, By is calculated as follows:

|  |  | By = Nsr x P x QNRBrepl. |  |  |
| --- | --- | --- | --- | --- |
| In which: |  |  |  |  |
| Nsr | The number of appliances. The parameter refers to the number of digesters in each size and category and is hence unitless. |  |  |  |
| P | Performance of digesters as the share of digesters implemented that is actually operational, determined through survey methods (%) |  |  |  |
| QNRBrepl. | Average quantity of biomass replaced per appliance and year (tonnes/year) |  |  |  |

Calculating the ERy for CPA-2

QNRBrepl.: 3.33 ton/year/appliance (ex-ante fixed)

P = 86.43 % (Calculated using user survey result: see ER calculation spreadsheet for actual value)

Nsr :  19,927 (database)

So, using equation above, By = 57,350.11  ton for monitoring period

Using the values:

fNRB,y: 86%

NCVbiomass: 0.015 TJ/tonne

EFprojected.fossilfuel:  81.6 tCO2/TJ

The value of ERy (using above eq) considering monitoring period of 127 days only (1 January 2021 to 7 May 2021) for this CP is calculated as 21,005.11 tCO2eq.

Similarly, substituting the values for,,,Nsr, P, and QNRBrepl from the above equations, the respective emission reduction for other CPAs are calculated as under:

CPA-3:  22,762.87 tCO2e (127 days under CP-1)

CPA-4:  22,192.96 tCO2e (127 days under CP-1)

CPA-5:  42,069.61 tCO2e (236 days under CP-1)

CPA-6:  56,703.17  tCO2e ( 1 years under the CP-1)

CPA-7:  53,629.46  tCO2e (1 year under the CP-1)

CPA-8:  62,481.18 tCO2e (1 year under the CP-1)

CPA-9:  57,082.79 tCO2e (1 year under the CP-1)

Total Baseline Emission Reduction: 337,927.16 tCO2e (1 year under the CP-1)

For Crediting Period 2 CP 2

As per the approved PDD, the formula for calculations of emission reduction is:

BEy = By x fNRB,y x NCVbiomass x EFprojected_fossilfuel

Where:

BEy			Baseline Emissions during the year y (tCO2e)

By	Quantity of woody biomass that is substituted or displaced in tonnes (tonnes/year)

fNRB,y	Fraction of woody biomass used in the absence of the project activity in year y that can be established as non-renewable biomass using survey methods	(Fixed Ex-ante = 86.1%)

NCVbiomass	Net calorific value of the non-renewable woody biomass that is substituted IPCC default for wood fuel: 0.0156 TJ/tonne)

EFprojected_fossilfuel	Emission factor for substitution of non-renewable woody biomass by similar consumers. Use a value of 63.7 tCO2/TJ

Calculation of Quantity of woody biomass that is substituted or displaced

The quantity of woody biomass that is substituted or displaced (By) is determined for CPA-1 by using:

By = NHH x Py x (BCBL,HH,y – BCPJ,HH,y)

| where, |  |
| --- | --- |
| NHH | : Number of digesters installed in the Project =19,999 |
| Py | : Percentage of digesters implemented that is operational in year y = 83.60 % |
| BCBL,HH,y | :Average annual consumption of woody biomass per household before the start of the project activity, 5.04 tonne/HH/year (fixed ex-ante) |
| BCPJ,HH,y | :Average annual consumption of woody biomass per household in the pre-project devices during the project activity, 0.51 tonne/HH/year (Monitored) |

By = 19,999 x 0.8360 x (5.04-0.51) = 75,737.81 tonnes

Considering the corresponding values for CPA-2, CPA-3, CPA-4, CPA-5 and CPA-10 with applicable monitoring period for CP-2 for corresponding CPAs, By are calculated below:

CPA-2: 51,322.37 tonnes (238 days)

CPA-3: 55,250.57 tonnes (238 days)

CPA-4: 54,105.41 tonnes (238 days)

CPA-5: 29,915.13 tonnes (129 days)

CPA-10: 39,391.46 tonnes (1 year)

Calculation of Baseline Emission

Considering the other parameters as given above, the baseline emission is calculated as below for CPA-1:

BEy for CPA-1:

= 75,737.81x 0.861 x 0.0156 x 63.7 = 64,800 tCO2eq

For remaining CPAs, baseline emission is calculated as below:

CPA-2: 43,911 tCO2eq

CPA-3: 47,271 tCO2eq

CPA-4: 46,292 tCO2eq

CPA-5: 25,595 tCO2eq

CPA-10: 33,703 tCO2eq

Total Emission: 261,572 tCO2eq

Total Emission Reduction from Crediting Period 1 and Crediting Period 2

| CPAs | Emission Reduction for Monitoring Period |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Crediting Period 1 (CP1) |  | Crediting Period 2 (CP2) |  | Total Emission Reduction |
|  | Emission Reduction | Monitoring Period | Leakage Estimation | Monitoring Period |  |
| CPA-1 | 0 | - | 61560 | 1 Jan 2021 to 31 Dec 2021 | 61560 |
| CPA-2 | 19954 | 1 Jan 2021 to 7 May 2021 | 41716 | 8 May 2021 to 31 Dec 2021 | 61670 |
| CPA-3 | 21624 | 1 Jan 2021 to 7 May 2021 | 44908 | 8 May 2021 to 31 Dec 2021 | 66532 |
| CPA-4 | 21083 | 1 Jan 2021 to 7 May 2021 | 43978 | 8 May 2021 to 31 Dec 2021 | 65061 |
| CPA-5 | 39966 | 1 Jan 2021 to 24 Aug 2021 | 24316 | 25 August to 31 Dec 2021 | 64282 |
| CPA-6 | 53868 | 1 Jan 2021 to 31 Dec 2021 |  |  | 53868 |
| CPA-7 | 50947 | 1 Jan 2021 to 31 Dec 2021 |  |  | 50947 |
| CPA-8 | 59357 | 1 Jan 2021 to 31 Dec 2021 |  |  | 59357 |
| CPA-9 | 54228 | 1 Jan 2021 to 31 Dec 2021 |  |  | 54228 |
| CPA-10 | 0 | - | 32018 | 1 Jan 2021 to 31 Dec 2021 | 32018 |

Baseline Estimates for SDG 3:

- 3.9.1 Mortality rate attributed to household and ambient air pollution (Users’ perception on reduction in indoor air pollution): 0% households (As using biomass for cooking)

- 3.9.1 Mortality rate attributed to household and ambient air pollution (Users’ perception on reduction in health problem): 0% households perceived in reduction of eye infection, respiratory disease, cough and fire related injury (as using biomass for cooking)

- 3.9.1 Mortality rate attributed to household and ambient air pollution (User’s perception in Time saving for the cooking (reduce exposure to indoor air pollution)): 0% households for men, women and children (as using biomass for cooking)

- 3.9.2 Mortality rate attributed to unsafe water, unsafe sanitation and lack of hygiene (exposure to unsafe Water, Sanitation and Hygiene for All (WASH) services) (Users’ perception on connection of toilet to biogas): 0% connection of toilet to Biogas as No biogas was used before project activity

- 3.9.3 Mortality rate attributed to unintentional poisoning (Users perception in reduction of chemical fertilizers): 0% reduction in use of chemical fertilizers (use of Farmyard manure, Bio-slurry, Urea, DAP and Potash) as using no biogas slurry.

Baseline Estimate for SDG 7:

- 7.1.2 Proportion of population with primary reliance on clean fuels and technology (Share of digesters operational): 0% as no bio-digester were implemented in baseline

- 7.1.2 Proportion of population with primary reliance on clean fuels and technology (Users’ perception on time saving due to project  for firewood collection): 0% households for men, women and children as no biogas was used in baseline

- 7.1.2 Proportion of population with primary reliance on clean fuels and technology (Trainings to Masons): 0 number

##### E.2. Calculation of project value or estimation of project situation of each SDG Impact

Project Estimate for SDG 13

Project emission (PEy) is considered as zero as this is not applicable for this project activity and accounted already in baseline emission.

Project Estimates for SDG 3:

1) 3.9.1 Mortality rate attributed to household and ambient air pollution (Users’ perception on reduction in indoor air pollution):

CPA-1: 97.61%

CPA-2: 100%

CPA-3: 97.77%

CPA-4: 93.26%

CPA-5: 98.90%

CPA-6: 97.70%

CPA-7: 96.43%

CPA-8: 100%

- CPA-9: 98.93%

CPA-10:100%

2) 3.9.1 Mortality rate attributed to household and ambient air pollution (Users’ perception on reduction in health problem):

| CPAs | % HH perceived reduction in |  |  |  |
| --- | --- | --- | --- | --- |
|  | Eye infection | Respiratory diseases | Cough | Fire related injury |
| CPA-1 | 94.05 | 89.29 | 86.90 | 91.67 |
| CPA-2 | 100 | 93.02 | 94.19 | 93.02 |
| CPA-3 | 98.92 | 90.32 | 89.25 | 93.55 |
| CPA-4 | 91.09 | 97.64 | 77.53 | 83.15 |
| CPA-5 | 97.80 | 93.41 | 90.11 | 100 |
| CPA-6 | 95.40 | 95.40 | 78.16 | 85.06 |
| CPA-7 | 95.24 | 88.10 | 88.10 | 88.10 |
| CPA-8 | 98.90 | 98.90 | 92.31 | 95.60 |
| CPA-9 | 97.80 | 88.30 | 88.30 | 88.30 |
| CPA-10 | 95.51 | 91.01 | 94.38 | 96.63 |

3) 3.9.1 Mortality rate attributed to household and ambient air pollution (User’s perception in Time saving for the cooking (reduce exposure to indoor air pollution)):

| CPAs | % HH perceived reduction in cooking time for |  |  |
| --- | --- | --- | --- |
|  | Men | Women | Children |
| CPA-1 | 40.48 | 98.81 | 17.86 |
| CPA-2 | 48.84 | 100 | 27.91 |
| CPA-3 | 25.81 | 96.77 | 21.51 |
| CPA-4 | 46.07 | 97.75 | 16.85 |
| CPA-5 | 36.26 | 100 | 29.67 |
| CPA-6 | 42.86 | 100 | 17.86 |
| CPA-7 | 38.10 | 100 | 25 |
| CPA-8 | 30.77 | 100 | 23.08 |
| CPA-9 | 51.06 | 100 | 19.15 |
| CPA-10 | 39.33 | 100 | 5.62 |

4) 3.9.2 Mortality rate attributed to unsafe water, unsafe sanitation and lack of hygiene (exposure to unsafe Water, Sanitation and Hygiene for All (WASH) services) (Users’ perception on connection of toilet to biogas):

CPA-1: 67.86 %

CPA-2: 74.42%

CPA-3: 63.44%

CPA-4: 89.89%

CPA-5: 85.71%

CPA-6: 87.36%

CPA-7: 79.76%

CPA-8: 85.71%

CPA-9: 79.79%

CPA-10: 96.63 %

5) 3.9.3 Mortality rate attributed to unintentional poisoning (Users perception in reduction of chemical fertilizers):

| CPAs | % changes in use of chemical fertilizers and increase in use of bio-slurry |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Farm Yard Manure | Bio-slurry | Urea | DAP | Potash |
| CPA-1 | 32.41 | 100 | 33.10 | 40.93 | 58.06 |
| CPA-2 | 28.68 | 100 | 38.54 | 0 | 50 |
| CPA-3 | 31.47 | 100 | 27.27 | 29.35 | 41.18 |
| CPA-4 | 30.62 | 100 | 37.42 | 0 | 58.62 |
| CPA-5 | 32.09 | 100 | 41.51 | 35.74 | 33.26 |
| CPA-6 | 30.65 | 100 | 35.52 | 36.65 | 46.43 |
| CPA-7 | 27.25 | 100 | 37.99 | 39.33 | 51.23 |
| CPA-8 | 28.59 | 100 | 25.66 | 28.23 | 33.33 |
| CPA-9 | 33.13 | 100 | 39.12 | 42.38 | 56.08 |
| CPA-10 | 32.59 | 100 | 31.36 | 50 | 0 |

Project Estimate for SDG 7:

- 7.1.2 Proportion of population with primary reliance on clean fuels and technology (Share of digesters operational):

CPA-1: 83.60%

CPA-2: 86.43%

CPA-3: 93.51%

CPA-4: 91.12%

CPA-5: 93.55%

CPA-6: 87.42%

CPA-7: 83.19%

CPA-8: 91.67%

CPA-9: 94.11%

CPA-10: 82.12%

- 7.1.2 Proportion of population with primary reliance on clean fuels and technology (Users’ perception on time saving due to project  for firewood collection):

| CPAs | % HH perceived reduction in firewood collection time for |  |  |
| --- | --- | --- | --- |
|  | Men | Women | Children |
| CPA-1 | 73.81 | 95.24 | 10.71 |
| CPA-2 | 65.12 | 98.84 | 29.07 |
| CPA-3 | 49.46 | 97.85 | 18.28 |
| CPA-4 | 65.17 | 98.88 | 15.73 |
| CPA-5 | 73.63 | 100 | 17.58 |
| CPA-6 | 83.93 | 100 | 14.29 |
| CPA-7 | 63.10 | 100 | 26.19 |
| CPA-8 | 62.64 | 98.90 | 7.69 |
| CPA-9 | 70.21 | 100 | 19.15 |
| CPA-10 | 49.44 | 98.88 | 5.62 |

- 7.1.2 Proportion of population with primary reliance on clean fuels and technology (Trainings to Masons): Not applicable however 75 mason trained in last MP

##### E.3. Calculation of leakage

Leakage Estimate for SDG 13

For Crediting Period 1 (CP 1)

The leakage is considered. Considering the leakage of 5% (as per the methodology AMS I.E. version 4), leakage emission is calculated as:

For CPA-2: LEy = 0.05 x ERy = 0.05 x 21,845.31 = 1,050.26 tCO2eq

Similarly, Leakage for other CPAs are:

CPA-3: 1,138.14 tCO2e (127 days under CP-1)

CPA-4: 1,109.65 tCO2e (127 days under CP-1)

CPA-5: 2,103.48 tCO2e (236 days under CP-1)

CPA-6: 2,835.16 tCO2e ( 1 years under the CP-1)

CPA-7: 2681.47 tCO2e ( 1 years under the CP-1)

CPA-8: 3,124.06 tCO2e ( 1 years under the CP-1)

CPA-9: 2,854.14 tCO2e ( 1 years under the CP-1)

Total Leakage: 16,896.36 tCO2e ( 1 years under the CP-1)

For Crediting Period 2 (CP2)

The leakage is considered. Considering the leakage of 5% (as per the methodology AMS I.E. version 9), leakage emission is calculated as:

For CPA-1:

LEy = 0.05 x BEy = 0.05 x 64,800 = 3,240 tCO2eq

Simlarly, leakage for other CPAs are given below:

CPA-2: 2,195 tCO2eq

CPA-3: 2,363 tCO2eq

CPA-4: 2,314 tCO2eq

CPA-5: 1,279 tCO2eq

CPA-10: 1,685 tCO2eq

Total Leakage: 13,076 tCO2eq

Total Leakage of Crediting Period 1 and Crediting Period 2:

| CPAs | Leakage Estimation for Monitoring Period |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Crediting Period 1 (CP1) |  | Crediting Period 2 (CP2) |  | Total Leakage Estimation |
|  | Leakage Estimation | Monitoring Period | Leakage Estimation | Monitoring Period |  |
| CPA-1 | - | - | 3,240.00 | 1 Jan 2021 to 31 Dec 2021 | 3,240 |
| CPA-2 | 1,050.26 | 1 Jan 2021 to 7 May 2021 | 2,195.00 | 8 May 2021 to 31 Dec 2021 | 3,245 |
| CPA-3 | 1,138.14 | 1 Jan 2021 to 7 May 2021 | 2,363.00 | 8 May 2021 to 31 Dec 2021 | 3,501 |
| CPA-4 | 1,109.65 | 1 Jan 2021 to 7 May 2021 | 2,314.00 | 8 May 2021 to 31 Dec 2021 | 3,424 |
| CPA-5 | 2,103.48 | 1 Jan 2021 to 24 Aug 2021 | 1,279.00 | 25 August to 31 Dec 2021 | 3,382 |
| CPA-6 | 2,835.16 | 1 Jan 2021 to 31 Dec 2021 |  |  | 2,835 |
| CPA-7 | 2,681.47 | 1 Jan 2021 to 31 Dec 2021 |  |  | 2,681 |
| CPA-8 | 3,124.06 | 1 Jan 2021 to 31 Dec 2021 |  |  | 3,124 |
| CPA-9 | 2,854.14 | 1 Jan 2021 to 31 Dec 2021 |  |  | 2,854 |
| CPA-10 | - | - | 1,685.00 | 1 Jan 2021 to 31 Dec 2021 | 1,685 |

Leakage Estimate for SDG 3

Leakage for the SDG 3 is taken as zero as it is not applicable.

Leakage Estimate for SDG 7

Leakage for the SDG 7 is taken as zero as it is not applicable.

##### E.4. Calculation of net benefits or direct calculation for each SDG Impact

| SDG | SDG Impact | Baseline estimate | Project estimate | Net benefit |
| --- | --- | --- | --- | --- |
| 13 | GHG emission (tCO2eq) | CPA-1 (CP2): 64,800.00 CPA-2 (CP1): 21,005.11 CPA-2 (CP2):43,911.00 CPA-3 (CP1): 22,762.87 CPA-3 (CP2):47,271.00 CPA-4 (CP1): 22,192.96 CPA-4 (CP2):46,292.00 CPA-5 (CP1): 42,069.61 CPA-5 (CP2): 25,595.00 CPA-6(CP1): 56,703.17 CPA-7(CP1): 53,629.46 CPA-8(CP1): 62,481.18 CPA-9(CP1): 57,082.79 CPA-10(CP1): 33,703.00 | CPA-1 (CP2): 3,240.00 CPA-2 (CP1): 1,050.26 CPA-2 (CP2): 2,195.00 CPA-3 (CP1): 1,138.14 CPA-3 (CP2): 2,363.00 CPA-4 (CP1): 1,109.65 CPA-4 (CP2): 2,314.00 CPA-5 (CP1): 2,103.48 CPA-5 (CP2): 1,279.00 CPA-6 (CP1): 2,835.16 CPA-7 (CP1): 2,681.47 CPA-8 (CP1): 3,124.06 CPA-9 (CP1): 2,854.14 CPA-10 (CP2):1,685.00 | CPA-1(CP2):61,560 CPA-2(CP1): 19,954 CPA-2(CP2): 41,716 CPA-3(CP1): 21,624 CPA-3(CP2): 44,908 CPA-4(CP1): 21,083 CPA-4(CP2): 43,978 CPA-5(CP1): 39,966 CPA-5(CP2): 24,316 CPA-6(CP1): 53,868 CPA-7(CP1): 50,947 CPA-8(CP1): 59,357 CPA-9(CP1): 54,288 CPA-10(CP2): 32,018 |
| 3 | 3.9.1 Mortality rate attributed to household and ambient air pollution (Users’ perception on reduction in indoor air pollution)-% | 0 | CPA-1: 97.61% CPA-2: 100% CPA-3: 97.77% CPA-4: 93.26% CPA-5: 98.90% CPA-6: 97.70% CPA-7: 96.43% CPA-8: 100% CPA-9: 98.93% CPA-10: 100% | CPA-1: 97.61% CPA-2: 100% CPA-3: 97.77% CPA-4: 93.26% CPA-5: 98.90% CPA-6: 97.70% CPA-7: 96.43% CPA-8: 100% CPA-9: 98.93% CPA-10: 100% |
|  | 3.9.1 Mortality rate attributed to household and ambient air pollution (Users’ perception on reduction in health problem)-% | 0 | CPA-1: Eye infection: 94.05%, Respiratory disease: 89.29% Cough: 86.90% Fire related Injury: 91.67% CPA-2: Eye infection: 100%, Respiratory disease: 93.02% Cough: 94.19% Fire related Injury: 93.02% CPA-3: Eye infection: 98.92% Respiratory disease: 90.32% Cough: 89.25% Fire related Injury: 93.55% CPA-4: Eye infection: 91.01% Respiratory disease: 97.64% Cough: 77.53% Fire related Injury: 83.15% CPA-5: Eye infection: 97.80% Respiratory disease: 93.41% Cough: 90.11% Fire related Injury: 100% CPA-6: Eye infection: 95.40% Respiratory disease: 95.40% Cough: 78.16% Fire related Injury: 85.06% CPA-7: Eye infection: 95.24% Respiratory disease: 88.10% Cough: 88.10% Fire related Injury: 88.10% CPA-8: Eye infection: 98.90% Respiratory disease: 98.90% Cough: 92.31% Fire related Injury: 95.60% CPA-9: Eye infection: 97.80% Respiratory disease: 88.30% Cough: 88.30% Fire related Injury: 88.30% CPA-10: Eye infection: 95.51% Respiratory disease: 91.01% Cough: 94.38% Fire related Injury: 96.63% | CPA-1: Eye infection: 94.05%, Respiratory disease: 89.29% Cough: 86.90% Fire related Injury: 91.67% CPA-2: Eye infection: 100%, Respiratory disease: 93.02% Cough: 94.19% Fire related Injury: 93.02% CPA-3: Eye infection: 98.92% Respiratory disease: 90.32% Cough: 89.25% Fire related Injury: 93.55% CPA-4: Eye infection: 91.01% Respiratory disease: 97.64% Cough: 77.53% Fire related Injury: 83.15% CPA-5: Eye infection: 97.80% Respiratory disease: 93.41% Cough: 90.11% Fire related Injury: 100% CPA-6: Eye infection: 95.40% Respiratory disease: 95.40% Cough: 78.16% Fire related Injury: 85.06% CPA-7: Eye infection: 95.24% Respiratory disease: 88.10% Cough: 88.10% Fire related Injury: 88.10% CPA-8: Eye infection: 98.90% Respiratory disease: 98.90% Cough: 92.31% Fire related Injury: 95.60% CPA-9: Eye infection: 97.80% Respiratory disease: 88.30% Cough: 88.30% Fire related Injury: 88.30% CPA-10: Eye infection: 95.51% Respiratory disease: 91.01% Cough: 94.38% Fire related Injury: 96.63% |
|  | 3.9.1 Mortality rate attributed to household and ambient air pollution (User’s perception in Time saving for the cooking (reduce exposure to indoor air pollution))-% | 0 | % response for; Men; Women; Children. CPA-1; 40.48; 98.81; 17.86. CPA-2; 48.84; 100; 27.91. CPA-3; 25.81; 96.77; 21.51. CPA-4; 46.07; 97.75; 16.85. CPA-5; 36.26; 100; 29.67. CPA-6; 42.86; 100; 17.86. CPA-7; 38.10; 100; 25. CPA-8; 30.77; 100; 23.08. CPA-9; 51.06; 100; 19.15. CPA-10; 39.33; 100; 5.62. | % response for; Men; Women; Children. CPA-1; 40.48; 98.81; 17.86. CPA-2; 48.84; 100; 27.91. CPA-3; 25.81; 96.77; 21.51. CPA-4; 46.07; 97.75; 16.85. CPA-5; 36.26; 100; 29.67. CPA-6; 42.86; 100; 17.86. CPA-7; 38.10; 100; 25. CPA-8; 30.77; 100; 23.08. CPA-9; 51.06; 100; 19.15. CPA-10; 39.33; 100; 5.62. |
|  | 3.9.2 Mortality rate attributed to unsafe water, unsafe sanitation and lack of hygiene (exposure to unsafe Water, Sanitation and Hygiene for All (WASH) services) (Users’ perception on connection of toilet to biogas)-% | 0 | CPA-1: 67.86% CPA-2: 74.42% CPA-3: 63.44% CPA-4: 89.89% CPA-5: 85.71% CPA-6: 87.36% CPA-7: 79.76% CPA-8: 85.71% CPA-9: 79.79% CPA-10: 96.63% | CPA-1: 67.86% CPA-2: 74.42% CPA-3: 63.44% CPA-4: 89.89% CPA-5: 85.71% CPA-6: 87.36% CPA-7: 79.76% CPA-8: 85.71% CPA-9: 79.79% CPA-10: 96.63% |
|  | 3.9.3 Mortality rate attributed to unintentional poisoning (Users perception in reduction of chemical fertilizers)-% | 0 | CPA-1: Farmyard manure: 32.41% Bioslurry: 100%, Urea: 33.10%, DAP: 40.39% Potash: 58.06% CPA-2: Farmyard manure: 28.68% Bioslurry: 100%, Urea: 38.54%, DAP: 0% Potash: 50.00% CPA-3: Farmyard manure: 31.47% Bioslurry: 100% Urea: 27.27% DAP: 29.35% Potash: 41.18% CPA-4: Farmyard manure: 30.62% Bioslurry: 100% Urea: 37.42% DAP: 0% Potash: 58.62% CPA-5 Farmyard manure: 32.09% Bioslurry: 100% Urea: 41.51% DAP: 35.74% Potash: 33.26% CPA-6: Farmyard manure: 30.65% Bioslurry: 100% Urea: 35.52% DAP: 36.65% Potash: 46.43% CPA-7: Farmyard manure: 27.25% Bioslurry: 100% Urea: 37.99% DAP: 39.33% Potash: 51.23% CPA-8: Farmyard manure: 28.59% Bioslurry: 100% Urea: 25.66% DAP: 28.23% Potash: 33.33% CPA-9: Farmyard manure: 33.13% Bioslurry: 100% Urea: 39.12% DAP: 42.38% Potash: 56.08% CPA-10: Farmyard manure: 32.59% Bioslurry: 100% Urea: 31.36% DAP: 50.00% Potash: 0% | CPA-1: Farmyard manure: 32.41% Bioslurry: 100%, Urea: 33.10%, DAP: 40.39% Potash: 58.06% CPA-2: Farmyard manure: 28.68% Bioslurry: 100%, Urea: 38.54%, DAP: 0% Potash: 50.00% CPA-3: Farmyard manure: 31.47% Bioslurry: 100% Urea: 27.27% DAP: 29.35% Potash: 41.18% CPA-4: Farmyard manure: 30.62% Bioslurry: 100% Urea: 37.42% DAP: 0% Potash: 58.62% CPA-5 Farmyard manure: 32.09% Bioslurry: 100% Urea: 41.51% DAP: 35.74% Potash: 33.26% CPA-6: Farmyard manure: 30.65% Bioslurry: 100% Urea: 35.52% DAP: 36.65% Potash: 46.43% CPA-7: Farmyard manure: 27.25% Bioslurry: 100% Urea: 37.99% DAP: 39.33% Potash: 51.23% CPA-8: Farmyard manure: 28.59% Bioslurry: 100% Urea: 25.66% DAP: 28.23% Potash: 33.33% CPA-9: Farmyard manure: 33.13% Bioslurry: 100% Urea: 39.12% DAP: 42.38% Potash: 56.08% CPA-10: Farmyard manure: 32.59% Bioslurry: 100% Urea: 31.36% DAP: 50.00% Potash: 0% |
| 7 | 7.1.2 Proportion of population with primary reliance on clean fuels and technology (Share of digesters operational) (%) | 0% | CPA-1:83.60% CPA-2: 86.43% CPA-3: 93.51% CPA-4: 91.12% CPA-5: 93.55% CPA-6: 87.42% CPA-7: 83.19% CPA-8: 91.67% CPA-9: 94.11% CPA-10: 82.12% | CPA-1:83.60% CPA-2: 86.43% CPA-3: 93.51% CPA-4: 91.12% CPA-5: 93.55% CPA-6: 87.42% CPA-7: 83.19% CPA-8: 91.67% CPA-9: 94.11% CPA-10: 82.12% |
|  | 7.1.2 Proportion of population with primary reliance on clean fuels and technology (Users’ perception on time saving due to project for firewood collection) | 0 | % for; Men; Women; Children. CPA-1; 73.81; 95.24; 10.71. CPA-2; 65.12; 98.84; 29.07. CPA-3; 49.46; 97.85; 18.28. CPA-4; 65.17; 98.88; 15.73. CPA-5; 73.63; 100; 17.58. CPA-6; 83.93; 100; 14.29. CPA-7; 63.10; 100; 26.19. CPA-8; 62.64; 98.90; 7.69. CPA-9; 70.21; 100; 19.15. CPA-10; 49.44; 98.88; 5.62. | % for; Men; Women; Children. CPA-1; 73.81; 95.24; 10.71. CPA-2; 65.12; 98.84; 29.07. CPA-3; 49.46; 97.85; 18.28. CPA-4; 65.17; 98.88; 15.73. CPA-5; 73.63; 100; 17.58. CPA-6; 83.93; 100; 14.29. CPA-7; 63.10; 100; 26.19. CPA-8; 62.64; 98.90; 7.69. CPA-9; 70.21; 100; 19.15. CPA-10; 49.44; 98.88; 5.62. |
|  | 7.1.2 Proportion of population with primary reliance on clean fuels and technology (Trainings to Masons) | 0 | 75 number in last MP | 75 number in last MP |

##### E.5. Comparison of actual SDG Impacts with estimates in approved PDD

| SDG | Values estimated in ex ante calculation of approved PDD for this monitoring period | Actual values achieved during this monitoring period |
| --- | --- | --- |
| 13: Emission Reduction | For Crediting Period 1 (CP1): CPA-2: 23,046 CPA-3: 23,079 CPA-4: 23,103 CPA-5: 42,598 CPA-6: 61,565 CPA-7: 61,191 CPA-8: 64,565 CPA-9: 57,134 For Crediting Period 2 (CP2): CPA-1: 61,560 CPA-2: 41,716 CPA-3: 44,908 CPA-4: 43,978 CPA-5: 24,316 CPA-10: 32,018 | CPA-2: 19,954 CPA-3: 21,624 CPA-4: 21,083 CPA-5: 39,966 CPA-6: 53,868 CPA-7: 50,947 CPA-8: 59,357 CPA-9: 54,228 CPA-1: 65,103 CPA-2: 42,297 CPA-3:42,366 CPA-4: 42,389 CPA-5: 22,828 CPA-10: 38,731 |
| 3: |  |  |
| 3.9.1 Mortality rate attributed to household and ambient air pollution (Users’ perception on reduction in indoor air pollution)-% | 100 | CPA-1: 97.61% CPA-2: 100% CPA-3: 97.77% CPA-4: 93.26% CPA-5: 98.90% CPA-6: 97.70% CPA-7: 96.43% CPA-8: 100% CPA-9: 98.93% CPA-10: 100% |
| 3.9.1 Mortality rate attributed to household and ambient air pollution (Users’ perception on reduction in health problem)-% | 100 | CPAs; % HH perceived reduction in. Eye infection; Respiratory diseases; Cough; Fire related injury. CPA-1; 94.05; 89.29; 86.90; 91.67. CPA-2; 100; 93.02; 94.19; 93.02. CPA-3; 98.92; 90.32; 89.25; 93.55. CPA-4; 91.09; 97.64; 77.53; 83.15. CPA-5; 97.80; 93.41; 90.11; 100. CPA-6; 95.40; 95.40; 78.16; 85.06. CPA-7; 95.24; 88.10; 88.10; 88.10. CPA-8; 98.90; 98.90; 92.31; 95.60. CPA-9; 97.80; 88.30; 88.30; 88.30. CPA-10; 95.51; 91.01; 94.38; 96.63. |
| 3.9.1 Mortality rate attributed to household and ambient air pollution (User’s perception in Time saving for the cooking (reduce exposure to indoor air pollution))-% | 100 | CPAs; % HH perceived reduction in cooking time for. Men; Women; Children. CPA-1; 40.48; 98.81; 17.86. CPA-2; 48.84; 100; 27.91. CPA-3; 25.81; 96.77; 21.51. CPA-4; 46.07; 97.75; 16.85. CPA-5; 36.26; 100; 29.67. CPA-6; 42.86; 100; 17.86. CPA-7; 38.10; 100; 25. CPA-8; 30.77; 100; 23.08. CPA-9; 51.06; 100; 19.15. CPA-10; 39.33; 100; 5.62. |
| 3.9.2 Mortality rate attributed to unsafe water, unsafe sanitation and lack of hygiene (exposure to unsafe Water, Sanitation and Hygiene for All (WASH) services) (Users’ perception on connection of toilet to biogas)-% | 100 | CPA-1: 67.86% CPA-2: 74.42% CPA-3: 63.44% CPA-4: 89.89% CPA-5: 85.71% CPA-6: 87.36% CPA-7: 79.76% CPA-8: 85.71% CPA-9: 79.79% CPA-10:96.63% |
| 3.9.3 Mortality rate attributed to unintentional poisoning (Users perception in reduction of chemical fertilizers)-% | 100 | CPAs; % changes in use of chemical fertilizers and increase in use of bio-slurry. Farm Yard Manure; Bio-slurry; Urea; DAP; Potash. CPA-1; 32.41; 100; 33.10; 40.39; 58.06. CPA-2; 28.68; 100; 38.54; 0; 50. CPA-3; 31.47; 100; 27.27; 29.35; 41.18. CPA-4; 30.62; 100; 37.42; 0; 58.62. CPA-5; 32.09; 100; 41.51; 35.74; 33.26. CPA-6; 30.65; 100; 35.52; 36.65; 46.43. CPA-7; 27.25; 100; 37.99; 39.33; 51.23. CPA-8; 28.59; 100; 25.66; 28.23; 33.33. CPA-9; 33.13; 100; 39.12; 42.38; 56.08. CPA-10; 32.59; 100; 31.36; 50.00; 0. |
| 7: |  |  |
| 7.1.2 Proportion of population with primary reliance on clean fuels and technology (Share of digesters operational) (%) | 100% | CPA-1:83.60% CPA-2: 86.43% CPA-3: 93.51% CPA-4: 91.12% CPA-5: 93.55% CPA-6: 87.42% CPA-7: 83.19% CPA-8: 91.67% CPA-9: 94.11% CPA-10: 82.12% |
| 7.1.2 Proportion of population with primary reliance on clean fuels and technology (Users’ perception on time saving due to project for firewood collection) | 100 | CPAs; % HH perceived reduction in firewood collection time for. Men; Women; Children. CPA-1; 73.81; 95.24; 10.71. CPA-2; 65.12; 98.84; 29.07. CPA-3; 49.46; 97.85; 18.28. CPA-4; 65.17; 98.88; 15.73. CPA-5; 73.63; 100; 17.58. CPA-6; 83.93; 100; 14.29. CPA-7; 63.10; 100; 26.19. CPA-8; 62.64; 98.90; 7.69. CPA-9; 70.21; 100; 19.15. CPA-10; 49.44; 98.88; 5.62. |
| 7.1.2 Proportion of population with primary reliance on clean fuels and technology (Trainings to Masons) | 20 throughout the PoA | 75 in last MP |

E.5.1. Explanation of calculation of value estimated ex ante calculation of approved PDD for this monitoring period

For Crediting Period 1 (CP1):

For the ex-ante calculation in CPA-DD, the equations given below were used where following assumption were made:

| In which: |  |
| --- | --- |
| ERy | Emissions Reductions during the year y (tCO2e) |
| By | Quantity of woody biomass that is substituted or displaced in tonnes |
| fNRB.y | Default value of fraction of non-renewable biomass for Nepal, |
| NCVbiomass | Net calorific value of the non-renewable woody biomass that is substituted |
| EFprojected.fossilfuel | Emission factor for substitution of non-renewable woody biomass by similar consumers. |

The quantity of woody biomass that is substituted or displaced (By) is determined using:

Thus, By is calculated as follows:

|  |  | By = Nsr x P x QNRBrepl. |  |  |
| --- | --- | --- | --- | --- |
| In which: |  |  |  |  |
| Nsr | The number of appliances. The parameter refers to the number of digesters in each size and category and is hence unitless. |  |  |  |
| P | Performance of digesters as the share of digesters implemented that is actually operational, determined through survey methods (%) |  |  |  |
| QNRBrepl. | Average quantity of biomass replaced per appliance and year (tonnes/year) |  |  |  |

Further, By is multiplied with a net to gross adjustment factor of 0.95 to account for leakage. Based on the assumptions below, annual ex-ante emission reduction are calculated for all CPA in CPA-DDs. Based on the number of days in the monitoring period, ex-ante emission reduction is proportionately calculated for the monitoring period.

| Parameters | CPA-2 | CPA-3 | CPA-4 | CPA-5 | CPA-6 | CPA-7 | CPA-8 | CPA-9 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Nsr | 19,927 | 19,959 | 19,970 | 19,842 | 18,504 | 18,392 | 19,445 | 17304 |
| P | 88.27% | 80.22% | 85.73% | 93.75% | 79.31% | 81.76% | 90.16% | 95.55% |
| QNRBrepl. | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 | 3.33 |
| fNRB,y | 86% | 86% | 86% | 86% | 86% | 86% | 86% | 86% |
| NCVbiomass | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 | 0.015 |
| EFprojected_fossilfuel | 81.6 | 81.6 | 81.6 | 81.6 | 81.6 | 81.6 | 81.6 | 81.6 |
| Annual Ex-ante (tCO2eq)/Year | 66,236 | 66,329 | 66,397 | 65,883 | 61,565 | 61,191 | 64,565 | 57134 |
| Ex-ante for MP (tCO2eq) | 23046 | 23079 | 23103 | 42598 | 61565 | 61191 | 64565 | 57134 |

For Crediting Period 2 (CP2):

For the ex-ante calculation in PoA DD, the following assumption were made:

BEy = By x fNRB,y x NCVbiomass x EFprojected_fossilfuel

Where:

Where:

BEy           : Baseline Emissions during the year y (tCO2e)

By	   : Quantity of woody biomass that is substituted or displaced in tonnes 			  (tonnes/year)

fNRB,y      : Fraction of woody biomass used in the absence of the project activity in       year y that can be established as non-renewable biomass using survey methods (Fixed Ex-ante = 86.1%)

NCVbiomass: Net calorific value of the non-renewable woody biomass that is substituted 	      (IPCC default for wood fuel: 0.0156 TJ/tonne)

EFprojected_fossilfuel : Emission factor for substitution of non-renewable woody biomass by similar consumers. Use a value of 63.7 tCO2/TJ

The quantity of woody biomass that is substituted or displaced (By) is determined using:

By = NHH x Py x (BCBL,HH,y – BCPJ,HH,y)

| where, |  |
| --- | --- |
| NHH | : Number of digesters installed in the Project |
| Py | : Percentage of digesters implemented that is operational in year y |
| BCBL,HH,y | :Average annual consumption of woody biomass per household before the start of the project activity, 5.04 tonne/household/year (fixed ex-ante) |
| BCPJ,HH,y | :Average annual consumption of woody biomass per household in the pre-project devices during the project activity, |

Considering the leakage of 5%, leakage emission is calculated as:

LEy = 0.05*BEy

Project Emission is considered as zero as this is not applicable. So, ex-ante emission reduction for this monitoring period is calculated as:

ERy = BEy-PEy-LEy

Based on the number of days in the monitoring period, ex-ante emission reduction is proportionately calculated for the monitoring period.

CPA-1: 65,103 tCO2eq (1 years)

CPA-2: 42,297 tCO2eq (238 days)

CPA-3: 42,366 tCO2eq (238 days)

CPA-4: 42,389 tCO2eq (238 days)

CPA-5: 22,828 tCO2eq (129 days)

CPA-10: 38,731 tCO2eq (1 year)

Total Ex ante Estimation for Monitoring Period 1st January 2021 – 31st December 2021

| CPAs | Ex ante Estimation Reduction for Monitoring Period |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
|  | Crediting Period 1 (CP1) |  | Crediting Period 2 (CP2) |  | Total Ex ante Emission Reduction |
|  | Ex ante Emission Reduction | Monitoring Period | Ex ante Emission Reduction | Monitoring Period |  |
| CPA-1 | - | - | 65,103 | 1 Jan 2021 to 31 Dec 2021 | 65,103 |
| CPA-2 | 23046 | 1 Jan 2021 to 7 May 2021 | 42,297 | 8 May 2021 to 31 Dec 2021 | 65,343 |
| CPA-3 | 23079 | 1 Jan 2021 to 7 May 2021 | 42,366 | 8 May 2021 to 31 Dec 2021 | 65,445 |
| CPA-4 | 23103 | 1 Jan 2021 to 7 May 2021 | 42,389 | 8 May 2021 to 31 Dec 2021 | 65,492 |
| CPA-5 | 42598 | 1 Jan 2021 to 24 Aug 2021 | 22,828 | 25 August to 31 Dec 2021 | 65,426 |
| CPA-6 | 61565 | 1 Jan 2021 to 31 Dec 2021 |  |  | 61,565 |
| CPA-7 | 61191 | 1 Jan 2021 to 31 Dec 2021 |  |  | 61,191 |
| CPA-8 | 64565 | 1 Jan 2021 to 31 Dec 2021 |  |  | 64,565 |
| CPA-9 | 57134 | 1 Jan 2021 to 31 Dec 2021 |  |  | 57,134 |
| CPA-10 | - | - | 38,731 | 1 Jan 2021 to 31 Dec 2021 | 38,731 |

##### E.6. Remarks on increase in achieved SDG Impacts from estimated value in approved PDD

Not applicable as the emission reduction has not been increased from ex-ante estimates in PDD.

#### SECTION F. SAFEGUARDS REPORTING

In monitoring plan, only one safeguarding principles have been incorporated to be monitored. Please refer to last parameter box is section D.2 of the MR. As per approved PoA-DD, the “Principles 9.6 Pesticides and fertilizers”, it is clearly mentioned that “Fertilisers shall be avoided, or their use shall be minimised and justified. If the aerial application of fertiliser is used, then measures shall be put in place to prevent drift.” Since, the project activity itself does not uses any chemical fertilizers but reduces its use in the farm by using bio-slurry. This has been monitored through a perception survey as stipulated in PoA-DD and found that the project activity significantly reduces the use of chemical fertilizers. Since other safeguarding principles are not attracted for the project activity for the mitigation measures and monitoring, the project has been appropriately aligned with the safeguarding principles.

#### SECTION G. STAKEHOLDER INPUTS AND LEGAL DISPUTES

##### G.1. List all Inputs and Grievances which have been received via the Continuous Input and Grievance Mechanism together with their respective responses/mitigations.

No any grievances/input was received during this monitoring period.

##### G.2. Report on any stakeholder mitigations that were agreed to be monitored.

Not applicable as there was no any grievances that need follow-up action from previous monitoring period.

##### G.3. Provide details of any legal contest that has arisen with the project during the monitoring period

No such legal disputes/contest has arisen during the monitoring period.

Revision History

| Version | Date | Remarks |
| --- | --- | --- |
| 1.1 | 14 October 2020 | Hyperlinked section summary to enable quick access to key sections Improved clarity on Key Project Information Section for POA monitoring Forward action request section Improved Clarity on SDG contribution/SDG Impact term used throughout Clarity on safeguard reporting Clarity on design changes Leakage section added for VER/CER projects Addition of Comparison of monitored parameters with last monitoring period Provision of an accompanying Guide to help the user understand detailed rules and requirements |
| 1.0 | 10 July 2017 | Initial adoption |

- http://cdm.unfccc.int/Projects/DB/RWTUV1321020993.82/view

- Whenever emission reductions are capped, both the original and capped values used for calculations must be transparently reported.  Use brackets to denote original values.